## Overall
ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress
__export__.project_task_400404_1d4bc74c | NGERP HQOW CENTRA | FA Depreciation Mapping - Branch field shows default value (*) | Sridhar S | Bugs | 2024-12-03 |  |  | 2024-12-03 14:31 | 0 | 2 | Resolved |  | 0
__export__.project_task_400199_166aac4e | NGERP HQOW CENTRA | #400199 - Master Credit Report (MTS) - write off Value mismatch for invoice and total amount | Thinesh Raajan S | Bugs | 2024-10-21 |  |  | 2024-11-26 15:26 | 0 | 11 | Resolved |  | 0
__export__.project_task_400073_ad3fe141 | NGERP HQOW CENTRA | #400073 - GENERAL LEDGER DETAIL report showing same data multiple time after process job | Thinesh Raajan S | Bugs | 2024-10-27 |  |  | 2024-11-12 17:43 | 0 | 5 | Resolved |  | 0
__export__.project_task_399997_29a84935 | NGERP HQOW CENTRA | #399997 - IMPORT Screens Issues | Manjula D | Bugs | 2024-07-08 |  |  | 2024-11-11 12:05 | 0 | 2 | Resolved |  | 0
__export__.project_task_399990_234738ac | NGERP HQOW CENTRA | Master Debit Report - Region report showing in HQ | Thinesh Raajan S | Bugs | 2024-11-09 |  |  | 2024-11-09 11:10 | 0 | 4 | Resolved |  | 0
__export__.project_task_399988_05871b75 | NGERP HQOW CENTRA | Daily Sales Report - Issues Listed | Thinesh Raajan S | Bugs | 2024-11-09 |  |  | 2024-11-09 11:01 | 0 | 5 | Resolved |  | 0
__export__.project_task_399946_7c933231 | NGERP HQOW CENTRA | Duplicate data showing in Import fee allocation report | Kishore R | Bugs | 2024-07-18 |  |  | 2024-11-07 18:32 | 0 | 16 | Resolved |  | 0
__export__.project_task_399929_a770461c | NGERP HQOW CENTRA | General Ledger report lines showing duplicate | Thinesh Raajan S | Bugs | 2024-10-21 |  |  | 2024-11-06 18:07 | 0 | 2 | Resolved |  | 0
__export__.project_task_399917_f4ddeb8a | NGERP HQOW CENTRA | Product Cost Queue and Cost details are not created after the MR is posted. | Kishore R | Bugs | 2024-07-24 |  |  | 2024-11-06 11:42 | 0 | 1 | Resolved |  | 0
__export__.project_task_399872_778977a8 | NGERP HQOW CENTRA | Payment Transaction Log parameter mismatch | Kishore R | Bugs | 2024-08-01 |  |  | 2024-11-05 11:16 | 0 | 0 | Resolved |  | 0
__export__.project_task_399847_caa64ee1 | NGERP HQOW CENTRA | #399847 - promotion unique reference SO transactions not import properly showing error | Mohideen Imthiaz S | Bugs | 2024-08-01 |  |  | 2024-11-04 18:18 | 0 | 2 | Resolved |  | 0
__export__.project_task_399844_4692a782 | NGERP HQOW CENTRA | Customer No salaes report missing some column's compar to AWS Centra and AWS R1 | Selvakumar S | Bugs | 2024-07-19 |  |  | 2024-11-04 17:34 | 0 | 0 | Resolved |  | 0
__export__.project_task_399830_bae74849 | NGERP HQOW CENTRA | 3A Channel, Customer code column values shows empty. | Sathish K | Bugs | 2024-11-04 |  |  | 2024-11-04 14:21 | 0 | 18 | Resolved |  | 0
__export__.project_task_399764_a2b1884a | NGERP HQOW CENTRA | Report - Role issue | Yogan P | Bugs | 2024-10-30 |  |  | 2024-10-30 10:48 | 0 | 4.5 | Resolved |  | 0
__export__.project_task_399755_8cf718db | NGERP HQOW CENTRA | Product Info warehouse loading issue. | Thinesh Raajan S | Bugs | 2024-10-29 |  |  | 2024-10-29 15:08 | 0 | 0 | Resolved |  | 0
__export__.project_task_399624_b86e6806 | NGERP HQOW CENTRA | Master Credit Report (MTS) - Value mismatch for invoice and total amount | Thinesh Raajan S | Bugs | 2024-10-21 |  |  | 2024-10-21 18:17 | 0 | 2 | Resolved |  | 0
__export__.project_task_399537_cec99a19 | NGERP HQOW CENTRA | Sales order DSO case not working when swtich login to different region. | Yogan P | Bugs | 2024-10-15 |  |  | 2024-10-15 15:38 | 0 | 0 | Resolved |  | 0
__export__.project_task_397379_d12e2cb5 | NGERP HQOW CENTRA | Manage PO Print – II ( PO_DenEast_Version2) Not working | Sridhar S | Bugs | 2024-07-26 |  |  | 2024-07-26 11:12 | 0 | 2 | Resolved |  | 0
__export__.project_task_397340_dc069798 | NGERP HQOW CENTRA | ( Inventory Move - ROW ) in Internal Transfer Print Format Not working. | Thinesh Raajan S | Bugs | 2024-07-25 |  |  | 2024-07-25 18:00 | 0 | 2 | Resolved |  | 0
__export__.project_task_397196_3d7e7b40 | NGERP HQOW CENTRA | New data not refelected in INVENTORY INOUT GIFT - HQ | Selvakumar S | Bugs | 2024-07-24 |  |  | 2024-07-24 10:50 | 0 | 4 | Resolved |  | 0
__export__.project_task_397157_ab92b4a4 | NGERP HQOW CENTRA | Branch Parameter not working in List of Commercial Discount - ROW | Thinesh Raajan S | Bugs | 2024-07-23 |  |  | 2024-07-23 13:47 | 0 | 2.5 | Resolved |  | 0
__export__.project_task_397113_ef4542df | NGERP HQOW CENTRA | Row report shows HQ Region data wrongly in Invoice Detail & Margin - ROW: | Sridhar S | Bugs | 2024-07-22 |  |  | 2024-07-22 18:41 | 0 | 8 | Resolved |  | 0
__export__.project_task_396911_3ba78c08 | NGERP HQOW CENTRA | Master Balance By Salesman(Monthly) Report filter not working | Sridhar S | Bugs | 2024-07-17 |  |  | 2024-07-17 18:10 | 0 | 10.5 | Resolved |  | 0
__export__.project_task_400144_8d4d3711 | NGERP HQOW CENTRA | Depreciation GL Header and line contain extra unused columns. | Yogan P | Bugs | 2024-11-21 |  |  | 2024-11-21 16:02 | 0 | 2 | Resolved |  | 0
__export__.project_task_400120_bd6be93f | NGERP HQOW CENTRA | 1st "Return to vendor" transaction completed with partial RMA qty. Need to Complete 2nd "Return to vendor" transaction with same RMA and remainging qty. But system could not able to process. | Selvakumar S | Bugs | 2024-11-19 |  |  | 2024-11-19 14:27 | 0 | 3 | Resolved |  | 0
__export__.project_task_398519_722bc928 | NGERP HQOW CENTRA | Customer RMA Screen issues listed. | Sathish K | Bugs | 2024-08-14 |  |  | 2024-08-14 11:41 | 0 | 6 | Resolved |  | 0
__export__.project_task_400192_ad6dd39d | NGERP HQOW CENTRA | Should not allow to reverse trade transaction in HQ | Sethupathy A | Bugs | 2024-11-26 |  |  | 2024-11-26 14:31 | 0 | 0 | Resolved |  | 0
__export__.project_task_399901_d23afe50 | NGERP HQOW CENTRA | Multi VAT Transfer no data is showing in screen. | Yogan P | Bugs | 2024-08-09 |  |  | 2024-11-05 16:45 | 0 | 0 | Resolved |  | 0
__export__.project_task_398482_5feaac5f | NGERP HQOW CENTRA | VAT Transfer - VAT Net Off Create Option Not working | Sethupathy A | Bugs | 2024-08-13 |  |  | 2024-08-13 11:48 | 0 | 0 | Resolved |  | 0
__export__.project_task_400072_db1614fe | NGERP HQOW CENTRA | #400072 - Trial Balance Reports Job process after check report showing multiple time same data centra applications issues | Thinesh Raajan S | Bugs | 2024-08-02 |  |  | 2024-11-12 17:19 | 0 | 5 | Resolved |  | 0
__export__.project_task_399900_fe5d7b1c | NGERP HQOW CENTRA | List of Commercial discount report not working in Centra HQ | Kishore R | Bugs | 2024-08-10 |  |  | 2024-11-05 16:27 | 0 | 0 | Resolved |  | 0
__export__.project_task_398060_284bf0a7 | NGERP HQOW CENTRA | Import Payment(HSBC) ACK | Thinesh Raajan S | Bugs | 2024-08-07 |  |  | 2024-08-09 15:43 | 0 | 2 | Resolved |  | 0
__export__.project_task_399420_2e668fb9 | NGERP HQOW CENTRA | Vendor RMA line Screen Tax field and quantity field should be editable. | Sridhar S | Bugs | 2024-10-04 |  |  | 2024-10-04 18:01 | 0 | 3 | Resolved |  | 0
__export__.project_task_400427_38d069b0 | NGERP HQOW CENTRA | CIP Resgiter import untick FAM Records in HQ Centra. | Sridhar S | Bugs | 2024-11-22 |  |  | 2024-12-04 11:08 | 0 | 0 | Resolved |  | 0
__export__.project_task_399547_09fc59cc | NGERP HQOW CENTRA | Attribute set instance field performance issue in All transaction screen. | Sathish K | Bugs | 2024-10-17 |  |  | 2024-10-17 12:01 | 0 | 1 | Resolved |  | 0
__export__.project_task_400405_93f72b50 | NGERP HQOW CENTRA | Import FA Register imports unticked FAM NTA AP invoice records. | Sridhar S | Bugs | 2024-08-07 |  |  | 2024-12-03 15:21 | 0 | 0 | Resolved |  | 0
__export__.project_task_399620_d2887c86 | NGERP HQOW CENTRA | Master Balance by Customer (Monthly) - Report loading continuously | Thinesh Raajan S | Bugs | 2024-07-23 |  |  | 2024-10-21 18:01 | 0 | 3 | Resolved |  | 0
__export__.project_task_399845_0eacf725 | NGERP HQOW CENTRA | Sales Order Summary Report(Merge report) 2 columns missing. | Sridhar S | Bugs | 2024-11-04 |  |  | 2024-11-04 17:37 | 0 | 0 | Resolved |  | 0

## Surya
ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project
__export__.project_task_400404_1d4bc74c | NGERP HQOW CENTRA | FA Depreciation Mapping - Branch field shows default value (*) | Sridhar S | Bugs | 2024-12-03 |  |  | 2024-12-03 14:31 | 0 | 2 | Resolved |  | 0
__export__.project_task_400199_166aac4e | NGERP HQOW CENTRA | #400199 - Master Credit Report (MTS) - write off Value mismatch for invoice and total amount | Thinesh Raajan S | Bugs | 2024-10-21 |  |  | 2024-11-26 15:26 | 0 | 11 | Resolved |  | 0
__export__.project_task_400073_ad3fe141 | NGERP HQOW CENTRA | #400073 - GENERAL LEDGER DETAIL report showing same data multiple time after process job | Thinesh Raajan S | Bugs | 2024-10-27 |  |  | 2024-11-12 17:43 | 0 | 5 | Resolved |  | 0
__export__.project_task_399997_29a84935 | NGERP HQOW CENTRA | #399997 - IMPORT Screens Issues | Manjula D | Bugs | 2024-07-08 |  |  | 2024-11-11 12:05 | 0 | 2 | Resolved |  | 0
__export__.project_task_399990_234738ac | NGERP HQOW CENTRA | Master Debit Report - Region report showing in HQ | Thinesh Raajan S | Bugs | 2024-11-09 |  |  | 2024-11-09 11:10 | 0 | 4 | Resolved |  | 0
__export__.project_task_399988_05871b75 | NGERP HQOW CENTRA | Daily Sales Report - Issues Listed | Thinesh Raajan S | Bugs | 2024-11-09 |  |  | 2024-11-09 11:01 | 0 | 5 | Resolved |  | 0
__export__.project_task_399946_7c933231 | NGERP HQOW CENTRA | Duplicate data showing in Import fee allocation report | Kishore R | Bugs | 2024-07-18 |  |  | 2024-11-07 18:32 | 0 | 16 | Resolved |  | 0
__export__.project_task_399929_a770461c | NGERP HQOW CENTRA | General Ledger report lines showing duplicate | Thinesh Raajan S | Bugs | 2024-10-21 |  |  | 2024-11-06 18:07 | 0 | 2 | Resolved |  | 0
__export__.project_task_399917_f4ddeb8a | NGERP HQOW CENTRA | Product Cost Queue and Cost details are not created after the MR is posted. | Kishore R | Bugs | 2024-07-24 |  |  | 2024-11-06 11:42 | 0 | 1 | Resolved |  | 0

## Vinesh
ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project
__export__.project_task_399872_778977a8 | NGERP HQOW CENTRA | Payment Transaction Log parameter mismatch | Kishore R | Bugs | 2024-08-01 |  |  | 2024-11-05 11:16 | 0 | 0 | Resolved |  | 0
__export__.project_task_399847_caa64ee1 | NGERP HQOW CENTRA | #399847 - promotion unique reference SO transactions not import properly showing error | Mohideen Imthiaz S | Bugs | 2024-08-01 |  |  | 2024-11-04 18:18 | 0 | 2 | Resolved |  | 0
__export__.project_task_399844_4692a782 | NGERP HQOW CENTRA | Customer No salaes report missing some column's compar to AWS Centra and AWS R1 | Selvakumar S | Bugs | 2024-07-19 |  |  | 2024-11-04 17:34 | 0 | 0 | Resolved |  | 0
__export__.project_task_399830_bae74849 | NGERP HQOW CENTRA | 3A Channel, Customer code column values shows empty. | Sathish K | Bugs | 2024-11-04 |  |  | 2024-11-04 14:21 | 0 | 18 | Resolved |  | 0
__export__.project_task_399764_a2b1884a | NGERP HQOW CENTRA | Report - Role issue | Yogan P | Bugs | 2024-10-30 |  |  | 2024-10-30 10:48 | 0 | 4.5 | Resolved |  | 0
__export__.project_task_399755_8cf718db | NGERP HQOW CENTRA | Product Info warehouse loading issue. | Thinesh Raajan S | Bugs | 2024-10-29 |  |  | 2024-10-29 15:08 | 0 | 0 | Resolved |  | 0
__export__.project_task_399624_b86e6806 | NGERP HQOW CENTRA | Master Credit Report (MTS) - Value mismatch for invoice and total amount | Thinesh Raajan S | Bugs | 2024-10-21 |  |  | 2024-10-21 18:17 | 0 | 2 | Resolved |  | 0
__export__.project_task_399537_cec99a19 | NGERP HQOW CENTRA | Sales order DSO case not working when swtich login to different region. | Yogan P | Bugs | 2024-10-15 |  |  | 2024-10-15 15:38 | 0 | 0 | Resolved |  | 0
__export__.project_task_397379_d12e2cb5 | NGERP HQOW CENTRA | Manage PO Print – II ( PO_DenEast_Version2) Not working | Sridhar S | Bugs | 2024-07-26 |  |  | 2024-07-26 11:12 | 0 | 2 | Resolved |  | 0

## Santhosh
ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project
__export__.project_task_397340_dc069798 | NGERP HQOW CENTRA | ( Inventory Move - ROW ) in Internal Transfer Print Format Not working. | Thinesh Raajan S | Bugs | 2024-07-25 |  |  | 2024-07-25 18:00 | 0 | 2 | Resolved |  | 0
__export__.project_task_397196_3d7e7b40 | NGERP HQOW CENTRA | New data not refelected in INVENTORY INOUT GIFT - HQ | Selvakumar S | Bugs | 2024-07-24 |  |  | 2024-07-24 10:50 | 0 | 4 | Resolved |  | 0
__export__.project_task_397157_ab92b4a4 | NGERP HQOW CENTRA | Branch Parameter not working in List of Commercial Discount - ROW | Thinesh Raajan S | Bugs | 2024-07-23 |  |  | 2024-07-23 13:47 | 0 | 2.5 | Resolved |  | 0
__export__.project_task_397113_ef4542df | NGERP HQOW CENTRA | Row report shows HQ Region data wrongly in Invoice Detail & Margin - ROW: | Sridhar S | Bugs | 2024-07-22 |  |  | 2024-07-22 18:41 | 0 | 8 | Resolved |  | 0
__export__.project_task_396911_3ba78c08 | NGERP HQOW CENTRA | Master Balance By Salesman(Monthly) Report filter not working | Sridhar S | Bugs | 2024-07-17 |  |  | 2024-07-17 18:10 | 0 | 10.5 | Resolved |  | 0
__export__.project_task_400144_8d4d3711 | NGERP HQOW CENTRA | Depreciation GL Header and line contain extra unused columns. | Yogan P | Bugs | 2024-11-21 |  |  | 2024-11-21 16:02 | 0 | 2 | Resolved |  | 0
__export__.project_task_400120_bd6be93f | NGERP HQOW CENTRA | 1st "Return to vendor" transaction completed with partial RMA qty. Need to Complete 2nd "Return to vendor" transaction with same RMA and remainging qty. But system could not able to process. | Selvakumar S | Bugs | 2024-11-19 |  |  | 2024-11-19 14:27 | 0 | 3 | Resolved |  | 0
__export__.project_task_398519_722bc928 | NGERP HQOW CENTRA | Customer RMA Screen issues listed. | Sathish K | Bugs | 2024-08-14 |  |  | 2024-08-14 11:41 | 0 | 6 | Resolved |  | 0
__export__.project_task_400192_ad6dd39d | NGERP HQOW CENTRA | Should not allow to reverse trade transaction in HQ | Sethupathy A | Bugs | 2024-11-26 |  |  | 2024-11-26 14:31 | 0 | 0 | Resolved |  | 0

## Gobi
ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress | ID | Project
__export__.project_task_399901_d23afe50 | NGERP HQOW CENTRA | Multi VAT Transfer no data is showing in screen. | Yogan P | Bugs | 2024-08-09 |  |  | 2024-11-05 16:45 | 0 | 0 | Resolved |  | 0
__export__.project_task_398482_5feaac5f | NGERP HQOW CENTRA | VAT Transfer - VAT Net Off Create Option Not working | Sethupathy A | Bugs | 2024-08-13 |  |  | 2024-08-13 11:48 | 0 | 0 | Resolved |  | 0
__export__.project_task_399900_fe5d7b1c | NGERP HQOW CENTRA | List of Commercial discount report not working in Centra HQ | Kishore R | Bugs | 2024-08-10 |  |  | 2024-11-05 16:27 | 0 | 0 | Resolved |  | 0
__export__.project_task_398060_284bf0a7 | NGERP HQOW CENTRA | Import Payment(HSBC) ACK | Thinesh Raajan S | Bugs | 2024-08-07 |  |  | 2024-08-09 15:43 | 0 | 2 | Resolved |  | 0
__export__.project_task_399420_2e668fb9 | NGERP HQOW CENTRA | Vendor RMA line Screen Tax field and quantity field should be editable. | Sridhar S | Bugs | 2024-10-04 |  |  | 2024-10-04 18:01 | 0 | 3 | Resolved |  | 0
__export__.project_task_400427_38d069b0 | NGERP HQOW CENTRA | CIP Resgiter import untick FAM Records in HQ Centra. | Sridhar S | Bugs | 2024-11-22 |  |  | 2024-12-04 11:08 | 0 | 0 | Resolved |  | 0
__export__.project_task_399547_09fc59cc | NGERP HQOW CENTRA | Attribute set instance field performance issue in All transaction screen. | Sathish K | Bugs | 2024-10-17 |  |  | 2024-10-17 12:01 | 0 | 1 | Resolved |  | 0
__export__.project_task_400405_93f72b50 | NGERP HQOW CENTRA | Import FA Register imports unticked FAM NTA AP invoice records. | Sridhar S | Bugs | 2024-08-07 |  |  | 2024-12-03 15:21 | 0 | 0 | Resolved |  | 0
__export__.project_task_399620_d2887c86 | NGERP HQOW CENTRA | Master Balance by Customer (Monthly) - Report loading continuously | Thinesh Raajan S | Bugs | 2024-07-23 |  |  | 2024-10-21 18:01 | 0 | 3 | Resolved |  | 0
__export__.project_task_399845_0eacf725 | NGERP HQOW CENTRA | Sales Order Summary Report(Merge report) 2 columns missing. | Sridhar S | Bugs | 2024-11-04 |  |  | 2024-11-04 17:37 | 0 | 0 | Resolved |  | 0

## Sheet6
ID | Description | Assigned | Status | feedback