## OVERALL
ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress
400396 | NGERP HQOW CENTRA | #400396 - Sales order screens after imported prom order created & updated by showing SuperUser it will show System in draft status of SO | Yogan P | Bugs | 45562 |  |  | 45628.7665 | 0 | 0 | Resolved |  | 0
399997 | NGERP HQOW CENTRA | #399997 - IMPORT Screens Issues | Manjula D | Bugs | 45481 |  |  | 45607.5035 | 0 | 2 | Resolved |  | 0
399847 | NGERP HQOW CENTRA | #399847 - promotion unique reference SO transactions not import properly showing error | Mohideen Imthiaz S | Bugs | 45505 |  |  | 45600.7624 | 0 | 2 | Resolved |  | 0
399844 | NGERP HQOW CENTRA | Customer No salaes report missing some column's compar to AWS Centra and AWS R1 | Selvakumar S | Bugs | 45492 |  |  | 45600.7318 | 0 | 0 | Resolved |  | 0
399830 | NGERP HQOW CENTRA | 3A Channel, Customer code column values shows empty. | Sathish K | Bugs | 45600 |  |  | 45600.5978 | 0 | 18 | Resolved |  | 0
399537 | NGERP HQOW CENTRA | Sales order DSO case not working when swtich login to different region. | Yogan P | Bugs | 45580 |  |  | 45580.6514 | 0 | 0 | Resolved |  | 0
400144 | NGERP HQOW CENTRA | Depreciation GL Header and line contain extra unused columns. | Yogan P | Bugs | 45617 |  |  | 45617.6684 | 0 | 2 | Resolved |  | 0
400437 | NGERP HQOW CENTRA | #400437 - Should allow to reverse trade transaction in centra regions (copy) | Sethupathy A | Bugs | 45622 |  |  | 45631.7425 | 0 | 0 | Resolved |  | 0
400072 | NGERP HQOW CENTRA | #400072 - Trial Balance Reports Job process after check report showing multiple time same data centra applications issues | Thinesh Raajan S | Bugs | 45506 |  |  | 45608.7214 | 0 | 5 | Resolved |  | 0
400430 | NGERP HQOW CENTRA | #400430 - Import DMS Order schedulerProcess Not propely showing msg | Yogan P | Bugs | 45510 |  |  | 45630.6664 | 0 | 0 | Resolved |  | 0
400431 | NGERP HQOW CENTRA | #400431 - NTA Payment shows error during import it will allow to create&complete payment by manually | Thinesh Raajan S | Bugs | 45618 |  |  | 45630.7523 | 0 | 0 | Resolved |  | 0
400230 | NGERP HQOW CENTRA | Master Balance by Customer (Daily) - ROW alignment issue | Yogan P | Bugs | 45496 |  |  | 45623.7299 | 0 | 0 | Resolved |  | 0
400174 | NGERP HQOW CENTRA | #400174 - Job roload completed for um_rv_bpartnerhistory_transaction_mv, so report show missing data | Thinesh Raajan S | Bugs | 45493 |  |  | 45621.5255 | 0 | 5 | Resolved |  | 0

## SANTHOSH
ID | Project | Assigned To | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress
400072 | NGERP HQOW CENTRA | Santhosh | #400072 - Trial Balance Reports Job process after check report showing multiple time same data centra applications issues | Thinesh Raajan S | Bugs | 2024-08-02 |  |  | 2024-11-12 17:19 | 0 | 5 | Resolved |  | 0
400430 | NGERP HQOW CENTRA | Santhosh | #400430 - Import DMS Order schedulerProcess Not propely showing msg | Yogan P | Bugs | 2024-08-06 |  |  | 2024-12-04 16:00 | 0 | 0 | Resolved |  | 0
400431 | NGERP HQOW CENTRA | Santhosh | #400431 - NTA Payment shows error during import it will allow to create&complete payment by manually | Thinesh Raajan S | Bugs | 2024-11-22 |  |  | 2024-12-04 18:03 | 0 | 0 | Resolved |  | 0
400230 | NGERP HQOW CENTRA | Santhosh | Master Balance by Customer (Daily) - ROW alignment issue | Yogan P | Bugs | 2024-07-23 |  |  | 2024-11-27 17:31 | 0 | 0 | Resolved |  | 0
400174 | NGERP HQOW CENTRA | Santhosh | #400174 - Job roload completed for um_rv_bpartnerhistory_transaction_mv, so report show missing data | Thinesh Raajan S | Bugs | 2024-07-20 |  |  | 2024-11-25 12:37 | 0 | 5 | Resolved |  | 0

## Summary
ID | Description | Assigned | Status | feedback
400072 |  | Santhsoh | Completed | Closed TL
400430 |  | Santhsoh | inprogress
400431 |  | Santhsoh | inprogress
400230 |  | Santhsoh | inprogress
400174 |  | Santhsoh | inprogress