## Sheet1
SNO | NAME | HQOW/ ROW | SB | SR | STATUS | IS SOURCE STOP | Assigned | DA Status | QA Status
1 | NTA FC BANK CHARGE INVOICE OF NTA AP INVOICE DOC SEQ ISSUE | HQOW | PURCHASE MANAGEMENT | NTA AP INVOICE | NYT COMPLETE | YES | mani |  | Done
2 | NON TRADE INVOICE DOC TYPE SHOWING IN AP INVOICE | HQOW | PURCHASE MANAGEMENT | NTA AP INVOICE | NYT COMPLETE | YES | Surya
3 | GAAP JOURNAL SEQ ISSUE | HQOW | ACCOUNTING MANAGEMENT | GL JOURNAL | NYT COMPLETE | YES | mani |  | Done
4 | GAAP CLOSING JOURNAL SEQ ISSUE * LOGIN | HQOW | ACCOUNTING MANAGEMENT | GL JOURNAL | NYT COMPLETE | YES | mani |  | Done
5 | FA REGISTER LINE -> NTA AP INVOICE NUMBER IS NOT CAPTURED THROWS ERROR ENTERED INVOICE SHOULD BE FAM. | HQOW | FAM | FA REGISTER | NYT COMPLETE | YES | kk
6 | DEPRECIATION PROCESS IS NOT SHOW IN * LOGIN. | HQOW | FAM | DEPRECIATION PROCESS | NYT COMPLETE | YES | kk
7 | CANNOT CREATE NEW CIP REGISTER, ITS LOADING MORE TIME. | HQOW | FAM | CIP REGISTER | NYT COMPLETE | YES | kk
8 | CIP REGISTER CANNOT VIEW ALREADY CREATED RECORDS. | HQOW | FAM | CIP REGISTER | NYT COMPLETE | YES | kk
9 | CANNOT CREATE FA DISPOSAL WRITEOFF LINE, ITS LOADING MORE TIME | HQOW | FAM | FA DISPOSAL WRITEOFF | NYT COMPLETE | YES | kk
10 | FA DISPOSAL WRITE OFF SEQUENCE ISSUE | HQOW | FAM | FA DISPOSAL WRITEOFF | NYT COMPLETE | YES | kk
11 | GL JOURNAL COULD NOT ALLOW TO IMPORT/CREATE DUE TO "COULD NOT SAVE JOURNAL - SAVEERRORNOTUNIQUE | HQOW | ACCOUNTING MANAGEMENT | GL JOURNAL | NYT COMPLETE | YES | kk
12 | GENERATE PAYMENT SUMMARY REPORT (NTA AP PAYMENT LOADING ISSUE SAME BPARTNER DIFF PAYMENT DATA | HQOW | ACCOUNTING MANAGEMENT | GENERATE PAYMENT SUMMARY REPORT | NYT COMPLETE | YES | hari |  | Done
13 | NTA AR INVOICE (DOC SEQ ISSUE | HQOW | SALES MANAGEMENT | NTA AR INVOICE | NYT COMPLETE | YES | mani |  | Done
14 | VIEW ALLOCATION REVERSE REGION TRANSACTION SHOW ERROR (PROCESS STILL LOAD | HQOW | ACCOUNTING MANAGEMENT | VIEW ALLOCATION | NYT COMPLETE | YES | mani |  | Done
15 | INVOICE (VENDOR SCREEN NOT AVAILABLE IN HQ.) | HQOW | PURCHASE MANAGEMENT | INVOICE (VENDOR) | NYT COMPLETE | YES | Surya
16 | NTA GOODS RECEIPT -> NOT ABLE TO COMPLETE | HQOW | PURCHASE MANAGEMENT | NTA GOODS RECEIPT | NYT COMPLETE | YES | Santhosh
17 | NTA PAYMENT ALLOCATION - AP -> INVOICE TO INVOICE ALLOCATION FAIL | HQOW | PURCHASE MANAGEMENT | NTA PAYMENT ALLOCATION AP | NYT COMPLETE | YES | hari |  | Done
18 | BATCH COMPLETE NTA AP INVOICE -> FOOTER COLUMN VALUE ISSUE | HQOW | PURCHASE MANAGEMENT | BATCH COMPLETE NTA AP INVOICE | NYT COMPLETE | YES | hari |  | Done
19 | GL JOURNAL -> NOT ABLE TO SAVE | HQOW | ACCOUNTING MANAGEMENT | GL JOURNAL | NYT COMPLETE | YES | hari |  | Done
20 | TREASURY MANAGEMENT -> NOT ABLE SAVE HEADER | HQOW | ACCOUNTING MANAGEMENT | TREASURY MANAGEMENT | NYT COMPLETE | YES | hari |  | Done
21 | VIEW ALLOCATION FOR NTA AP INVOICE -> NOT POSTED | HQOW | ACCOUNTING MANAGEMENT | VIEW ALLOCATION | NYT COMPLETE | YES | Surya
22 | MASTER INVENTORY GIFT -> REPORT MISSING IN ROW | HQOW | INVENTORY MANAGMENT | MASTER INVENTORY GIFT | NYT COMPLETE | YES | Vinesh
23 | ACCRUAL FOC -> LINE SAVE ISSUE | HQOW | ACCOUNTING MANAGEMENT | ACCRUAL FOC | NYT COMPLETE | YES | hari |  | Done
24 | NTA AP INVOICE -> WRONG DOCUMENT SEQUENCE | HQOW | PURCHASE MANAGEMENT | NTA AP INVOICE | NYT COMPLETE | YES | hari |  | Done
25 | NTA PAYMENT - AP -> WRONG DOCUMENT SEQUENCE FOR NETOFF RECEIPT, INTERBRANCH RECEIPT | HQOW | PURCHASE MANAGEMENT | NTA PAYMENT – AP | NYT COMPLETE | YES | hari |  | Done
26 | MANAGE INVOICE MULTI CAMPGIN BUTTON MISSING | ROW | SALES MANAGEMENT | MANAGE INVOICE | NYT COMPLETE | YES | mani |  | Done
27 | BRANCH TRANSFER CONFIRMATION NHA TRANG COMPLETE BUTTON NOT ENABLE | ROW | INVENTORY MANAGMENT | BRANCH TRANSFER CONFIRMATION | NYT COMPLETE | YES | mani |  | Done
28 | INTERNAL TRANSFER NHA TRANG NEW BUTTON NOT ENABLE | ROW | INVENTORY MANAGMENT | INTERNAL TRANSFER | NYT COMPLETE | YES | Vinesh
29 | PRINT BATCH INVOICE FORM PRINT ITT CHECK BOX MISSING NHA TRANG | ROW | SALES MANAGEMENT | PRINT BATCH INVOICE | NYT COMPLETE | YES | mani |  | Done
30 | IMPORT CASH PAYMENT --> "PROCESS" BUTTON NOT ENABLED | ROW | SALES MANAGEMENT | IMPORT CASH PAYMENT | NYT COMPLETE | YES | kk
31 | IMPORT PAYMENT OUT AR --> COMPLETED BUTTON NOT ENABLED | ROW | SALES MANAGEMENT | IMPORT PAYMENT OUT AR | NYT COMPLETE | YES | kk
32 | IMPORT INCIDENT CHARGE INVOICE --> "PROCESS" BUTTON NOT ENABLED | ROW | PURCHASE MANAGEMENT | IMPORT INCIDENT CHARGE INVOICE | NYT COMPLETE | YES | kk
33 | IMPORT INTERNAL TRANSFER INVOICE --> "PROCESS" BUTTON NOT ENABLED | ROW | INVENTORY MANAGMENT | IMPORT INTERNAL TRANSFER INVOICE | NYT COMPLETE | YES | kk
34 | IMPORT CONSIGNMENT ORDER --> "PROCESS" BUTTON NOT ENABLED. | ROW | INVENTORY MANAGMENT | IMPORT CONSIGNMENT ORDER | NYT COMPLETE | YES | kk
35 | PROMOTION ORDER TESTING - NOT COMPLETE (NEED FTP PATH CONFIGURATION) | ROW | SALES MANAGEMENT | SALES ORDER | NYT COMPLETE | YES | mani/hari |  | NOT FIXED
36 | AR INVOICE SCREEN ROW LOGIN SHOWING POST BUTTON | ROW | SALES MANAGEMENT | MANAGE INVOICE | NYT COMPLETE | YES | Vinesh
37 | DO FROM SO FORM SHOWING NTA WAREHOUSE | ROW | SALES MANAGEMENT | MANAGE DO | NYT COMPLETE | NO | Vinesh
38 | VIEW ALLOCATION REGION LOGIN SHOWING NTA AP INVOICE DATA | ROW | SALES MANAGEMENT | VIEW ALLOCATION | NYT COMPLETE | YES | Santhosh
39 | BATCH COMPLETE AR PAYMENT ONLY PROCESS 20 DATA | ROW | SALES MANAGEMENT | BATCH COMPLETE AR PAYMENT | NYT COMPLETE | YES | mani |  | Done
40 | VIEW ALLOCATINO CAN'T REVERSE IN ROW (ROW DATA (1946560)) | ROW | SALES MANAGEMENT | VIEW ALLOCATION | NYT COMPLETE | YES | mani |  | Done
41 | INVOICE WRITE OFF SCHEDULER SHOW 500 ERROR | ROW | SALES MANAGEMENT | INVOICE WRITE OFF SCHEDULER | NYT COMPLETE | YES | mani |  | Done
42 | CUSTOMER RETURN CREATE RETURN LINES FROM BUTTON NOT WORKED, COMPANY COLUMN NAME NOT SHOW | ROW | SALES MANAGEMENT | CUSTOMER RETURN | NYT COMPLETE | YES | Santhosh
43 | BATCH COMPLETE AP PAYMENT FORM MISSING ROW | ROW | PURCHASE MANAGEMENT | BATCH COMPLETE AP PAYMENT | NYT COMPLETE | YES | mani |  | Done
44 | MASTER INVENTORY REPORT Â€“ PACKAGE - ROW - REPORT NAME MISMATCH | ROW | INVENTORY MANAGMENT | MASTER INVENTORY REPORT | NYT COMPLETE | NO | Santhosh
45 | MASTER INVENTORY REPORT Â€“ PACKAGE - ROW REPORT COULD NOT ALLOW TO OPEN DUE TO ROLE ISSUE | ROW | INVENTORY MANAGMENT | MASTER INVENTORY REPORT – PACKAGE | NYT COMPLETE | NO | Surya |  | NOT FIXED
46 | PO DOCUMENT NO NOT LOADING IN VENDOR RMA SCREEN | ROW | PURCHASE MANAGEMENT | VENDOR RMA | NYT COMPLETE | YES | hari |  | NOT FIXED
47 | MANAGE DO PRINT FORMAT ISSUE (R6 & R7 REGION) | ROW | SALES MANAGEMENT | MANAGE DO | NYT COMPLETE | YES | hari |  | NOT FIXED
48 | PO ALOG & NOLA PRINT FORMAT 5 COLUMNS VALUE NOT LOADING ISSUE | ROW | PURCHASE MANAGEMENT | PURCHASE ORDER | NYT COMPLETE | YES | hari |  | Done
49 | IMPORT CIP AND IMPORT FA REGISTER SCREEN DATA LOADING ISSUE | HQOW | FAM | IMPORT CIP AND IMPORT FA REGISTER | NYT COMPLETE | YES | hari |  | NOT FIXED