## Forms63_05-10Aug
# | SB | Service Request – Macro | Service Request – Micro | HQOW / ROW / FAM | Tables | Classes Used | SQL View Used | AD Impact | FITGAP (Compiere / NGERP) | 3R – KMM & MIW | Estimate | AssignedTo | QA | ADScript/CODE | Release Date | QA Completion Date
23 | FORM | Account mapping Combination | Account mapping Combination | HQOW | C_ValidCombination,AD_Org,C_ElementValue | AccountEditorWindowImpl.java |  | Yes | NGERP | KEEP | 2 | Sridhar | Manjula |  | 07August2024
62 | FORM | AttributeInfo-Trade | AttributeInfo-Trade | ROW | M_Locator,M_Warehouse,M_Product,C_Bpartner | PattributeInstanceWindowImpl.java |  | No | Compiere | MOVE | 16 | Yogan | Manirathnam |  | 07August2024 | 23August2024
25 | FORM | Bad Debt Written Off | Bad Debt Written Off | ROW | C_Payment_v,C_Currency,C_Invoice_v | BadDebtWrittenOffWindowImpl.java, BadDebtWrittenOffWindow.java |  | Yes | NGERP | MOVE | 16 | Imthiaz | Manirathnam |  | 05August2024 | 23August2024
20 | FORM | Bank Statement-CreateLinesFrom | Bank Statement-CreateLinesFrom | HQOW | C_BankAccount,C_Payment_v,C_Currency,C_Bpartner | CreateFromStatementWindowImpl.java |  | Yes | NGERP | KEEP | 2 | Sathish | Venkat |  | 06August2024 | 26August2024
26 | FORM | Batch Complete AR Payment | Batch Complete AR Payment | ROW | C_PAYMENT,C_BPARTNER,AD_ORG | BatchCompleteARPaymentWindowImpl.java |  | Yes | NGERP | MOVE | 16 | Sathish | Manirathnam |  | 06August2024 | 23August2024
27 | FORM | Batch Complete Cash Payment | Batch Complete Cash Payment | ROW | c_Payment,C_BPARTNER, c_bp_group,AD_ORG | BatchCompleteCashPaymentWindowImpl.java |  | Yes | NGERP | MOVE | 16 | Sathish | Manirathnam |  | 05August2024 | 23August2024
6 | FORM | Batch Complete Commercial Discount | Batch Complete Commercial Discount | HQOW | UM_CommDiscount,C_Campaign,AD_ORG,c_year | BatchCompleteCommercialDiscountWindowImpl.java,BatchCompleteCommercialDiscountWindow.java |  | Yes | NGERP | KEEP | 2 | Jegan | Hari |  | 05August2024 | 20August2024
28 | FORM | Batch Complete DSO Order | Batch Complete DSO Order | ROW | c_order,C_BPARTNER,c_bp_group,AD_ORG,UM_CustomerProgram | BatchCompleteDSOWindowImpl.java |  | Yes | NGERP | MOVE | 16 | Sathish | Manirathnam |  | 05August2024 | 23August2024
11 | FORM | Batch Complete NTA AP Payments | Batch Complete NTA AP Payments | HQOW | C_PAYMENT,C_BPARTNER,AD_ORG | BatchCompleteNTAAPPaymentWindowImpl.java,BatchCompleteNTAAPPaymentWindow.java |  | Yes | NGERP | KEEP | 2 | Yogan | KK |  | 05August2024 | 19August2024
3 | FORM | Batch Complete Payment NetOff | Batch Complete Payment NetOff | HQOW | c_Payment,C_BPARTNER, C_Campaign,AD_ORG,c_year | BatchCompletePaymentNetOffWindowImpl.java, BatchCompletePaymentNetOffWindow.java |  | Yes | NGERP | KEEP | 2 | Sathish | Manirathnam |  | 07August2024 | 22August2024
29 | FORM | Batch Complete Payment-AP | Batch Complete Payment-AP | ROW |  | BatchCompleteAPPaymentWindowImpl.java |  | Yes | NGERP | MOVE | 16 | Sathish | Manirathnam |  | 05August2024 | 23August2024
30 | FORM | Batch Complete Promotion Order | Batch Complete Promotion Order | ROW | c_order,C_BPARTNER,c_bp_group,AD_ORG,UM_CustomerProgram | BatchCompleteSOWindowImpl.java |  | Yes | NGERP | MOVE | 16 | Sethu | Manirathnam |  | 07August2024 | 23August2024
31 | FORM | Batch Confirm Complete | Batch Confirm Complete | ROW | M_InoutConfirm,AD_Org,M_Inout,C_Order | GenerateConfirmWindowImpl.java, GenerateConfirmWindow.java |  | Yes | NGERP | MOVE | 16 | Sethu | Manjula |  | 07August2024
32 | FORM | Batch Sales Order Approval | Batch Sales Order Approval | ROW | c_order,C_BPARTNER,c_bp_group,AD_ORG,UM_SubChannel,m_warehouse,UM_CustomerProgram | BatchSalesOrderApprovalWindowImpl.java |  | Yes | NGERP | MOVE | 16 | Sethu | Manjula |  | 07August2024
17 | FORM | bpartnerInfo | bpartnerInfo | HQOW + ROW | C_Greeting,C_Bpartner,UM_PartnerGroup | InfoBPartnerWindowImpl.java |  | No | Compiere | MERGE | 16 | Imthiaz | Manirathnam |  | 07August2024 | 23August2024
58 | FORM | BpartnerInfo-Trade | BpartnerInfo-Trade | HQOW + ROW | C_Greeting,C_Bpartner,UM_PartnerGroup | BusinessPartnerWindowImpl.java |  | No | Compiere | MERGE | 16 | Selva | Venkat |  | 07August2024 | 23August2024 | KK
33 | FORM | Confirm DMS Export | Confirm DMS Export | ROW | c_invoice,ad_org,c_order,rv_openitemdms | ConfirmDMSExportWindowImpl.java |  | Yes | NGERP | MOVE | 16 | Sethu | Manjula |  | 08August2024
56 | FORM | CreateFromInvoice | CreateFromInvoice | ROW | c_order,C_OrderLine,M_MatchPO,M_Product,C_Charge,C_Campaign, um_subactivity,c_activity | CreateFromInvoiceWindowImpl.java |  | No | Compiere | MOVE | 16 | Jegan | Venkat |  | 09August2024 | 26August2024
57 | FORM | CreateFromPOI | CreateFromPOI | ROW | c_order,c_currency,ad_org,c_order,c_orderline,c_invoice,c_invoiceline | CreateFromPOInvoiceWindowImpl.java |  | No | Compiere | MOVE | 16 | Selva | Venkat |  | 09August2024 | 26August2024 | KK
55 | FORM | CreateFromShipment | CreateFromShipment | ROW | C_BPConsignedLocator,um_C_Order,C_OrderLine,M_MatchPO,um_c_orderline,m_inoutline,m_inout | CreateFromShipmentWindowImpl.java |  | No | Compiere | MOVE | 16 | Jegan | Venkat |  | 08August2024 | 26August2024 | KK
60 | FORM | CreateFromStatement | CreateFromStatement | HQOW | C_BankAccount,C_Payment_v,C_Currency,C_Bpartner,M_payment | CreateFromStatementWindowImpl.java |  | No | Compiere | MOVE | 16 | Sridhar | Venkat |  | 05August2024 | 23August2024 | KK
34 | FORM | DO Print Batch Invoice | DO Print Batch Invoice | ROW | C_Invoice,AD_Org,C_DocType,C_Bpartner,C_BP_GROUP,AD_OrgInfo,AD_User,C_BP_BANKACCOUNT,C_BANK,UM_RejectionCode | DAPrintBatchInvoiceWindowImpl.java |  | Yes | NGERP | MOVE | 16 | Sridhar | Manjula |  | 05August2024 |  | KK
10 | FORM | ExportBatch AP City Report | ExportBatch AP City Report | HQOW | c_invoice,c_bpartner,c_invoiceline,c_allocationhdr,c_allocationline,m_inout,m_inoutline | ExportBatchAPCitiReportWindowImpl.java, ReportServiceImpl.java,ExportBatchAPCitiReportWindow.java, ExportAPCitiReport.java ZoomAcrossServiceImpl.java, ZoomAcrossServiceAsync.java, ZoomAcrossService.java |  | Yes | NGERP | KEEP | 2 | Sridhar | Hari |  | 07August2024 | 21August2024
35 | FORM | Generate AP Payment | Generate AP Payment | ROW | c_invoice,c_bpartner,ad_org,C_Currency,c_payment,c_allocationline,c_allocationhdr,c_bp_bankaccount | GenerateAPPaymentWindowImpl.java |  | Yes | NGERP | MOVE | 16 | Sridhar | Manjula |  | 05August2024
24 | FORM | Generate Charges | Generate Charges | HQOW | C_Charge | GenerateChargesWindowImpl.java |  | Yes | Compiere | KEEP | 2 | Selva | Manjula |  | 06August2024 | 20August2024
36 | FORM | Generate DO From SO | Generate DO From SO | ROW | c_order,C_DocType,c_orderline,AD_Org,M_Warehouse,C_Bpartner,C_BPARTNER_LOCATION,C_Location,UM_CustomerProgram,m_inoutline,m_inout | GenerateShipmentWindowImpl.java, GenerateShipmentWindow.java |  | Yes | NGERP | MOVE | 16 | Sridhar | Manjula |  | 06August2024 | 20August2024
37 | FORM | Generate Invoices From SO | Generate Invoices From SO | ROW | C_Order,C_OrderLine,AD_Org,C_Bpartner,C_DocType | GenerateInvoiceWindowImpl.java, GenerateInvoiceWindow.java |  | Yes | NGERP | MOVE | 16 | Sridhar | Manjula |  | 06August2024 | 20August2024
12 | FORM | Generate Payment Summary Report | Generate Payment Summary Report | HQOW | C_Payment,AD_Org,C_Currency,C_Bpartner,C_BP_BankAccount,GL_Journal,GL_Journalline, c_validcombination | GeneratePaymentSummaryReportWindowImpl.java,GeneratePaymentSummaryReportWindow.java |  | Yes | NGERP | KEEP | 2 | Yogan | KK |  | 05August2024 | 22August2024
38 | FORM | Generate Picking List Summary | Generate Picking List Summary | ROW | M_InoutLine,M_Inout,C_Order,C_UOM_Conversion,M_InoutConfirm,C_Order,AD_User,M_Warehouse,C_BPartner,C_BPartner_Location,C_Location,C_BP_Group, C_Region , UM_Route,W_Rate | GeneratePickingListSummaryWindowImpl.java, GeneratePickingListSummaryWindow.java |  | Yes | NGERP | MOVE | 16 | Yogan | Manjula |  | 06August2024
63 | FORM | Generate Transfer CIP To FA | Generate Transfer CIP To FA | FAM | UM_CIPRegister,M_Product,M_Product_Category_Acct,C_ValidCombination,C_elementValue,C_Activity,M_TransferCIPLine,M_TransferCIP | GenerateTransferCIPWindowImpl.java |  | No | NGERP | MOVE | 16 | Sethu | Manjula |  | 08August2024
5 | FORM | Generate Transport Manifest | Generate Transport Manifest | HQOW | m_inout,C_BPartner,m_inoutline,m_product,C_BPartner_Location, C_Location,C_BP_Group,C_Region,UM_Route | GenerateTransportManifestwindowimpl.java,GenerateTransportManifestwindowimpl.java |  | Yes | NGERP | KEEP | 2 | Selva | Manirathnam |  | 05August2024 | 23August2024
39 | FORM | Generate Transport Manifest | Generate Transport Manifest | ROW | m_inout,C_Bpartner,m_inoutline,m_product,C_Bpartner_Location,C_Location,C_BP_Group,C_Region,UM_Route | GenerateTransportManifestwindowimpl.java, GenerateTransportManifestwindow.java |  | Yes | NGERP | MOVE | 16 | Yogan | Venkat |  | 08August2024 | 26August2024
9 | FORM | Generate Treasury Encryption | Generate Treasury Encryption | HQOW | gl_journal,ad_attachment | GenerateTreasuryEncryptionWindowImpl.java,GenerateTreasuryEncryptionWindow.java |  | Yes | NGERP | KEEP | 2 | Sridhar | Hari |  | 07August2024 | 20August2024
22 | FORM | Goods Receipt CreateLinesFrom | Goods Receipt CreateLinesFrom | HQOW | c_order,C_OrderLine,M_MatchPO,M_Product,C_Charge,C_Campaign, um_subactivity,c_activity | CreateFromNTAGRWindowImpl.java |  | Yes | NGERP | KEEP | 2 | Thinesh | Venkat |  | 07August2024 | 23August2024
40 | FORM | Import File Loader | Import File Loader | ROW |  | ImportFileLoaderWindowImpl.java, GenerateTransportManifestwindow.java |  | Yes | NGERP | MOVE | 16 | Yogan | Hari |  | 07August2024 | 21August2024
61 | FORM | LocationInfo | LocationInfo | ROW | M_Locator,M_Warehouse | InfoLocatorWindowImpl.java |  | No | Compiere | MOVE | 16 | Kishore | Venkat |  | 08August2024 | 23August2024
8 | FORM | Multi VAT Transfer | Multi VAT Transfer | HQOW | C_Invoice,UM_VATTransfer | MultiVatTransferWindowImpl.java,VVATInGenerate.java,MultiVatTransferWindow.java |  | Yes | NGERP | KEEP | 2 | Sethu | Hari |  | 05August2024 | 20August2024
41 | FORM | Multi VAT Transfer | Multi VAT Transfer | ROW | c_bpartner,UM_VATTransfer,C_Invoice | VATInGenerateWindowImpl.java |  | Yes | NGERP | MOVE | 16 | Yogan | KK |  | 07August2024 | 23August2024
1 | FORM | NTA AP Invoice Batch | NTA AP Invoice Batch | HQOW | C_invoice,C_BPARTNER, AD_ORG | BatchCompleteNTAAPInvoiceWindowImpl.java,BatchCompleteNTAAPInvoiceWindowImpl.java |  | Yes | NGERP | KEEP | 2 | Imthiaz | Manirathnam |  | 05August2024 | 22August2024 | Hari
2 | FORM | NTA AP Invoice Batch Approval | NTA AP Invoice Batch Approval | HQOW | C_invoice,C_BPARTNER,AD_ORG,c_year | BatchCompleteNTAAPInvoiceApprovalWindowImpl.java,BatchCompleteNTAAPInvoiceApprovalWindow.java |  | Yes | NGERP | KEEP | 2 | Imthiaz | Manirathnam |  | 06August2024 | 22August2024
21 | FORM | NTA AP Invoice createLinesFrom | NTA AP Invoice createLinesFrom | HQOW | c_order,C_OrderLine,M_MatchPO,M_Product,C_Charge,C_Campaign, um_subactivity,c_activity | CreateFromNTAInvoiceWindowImpl.java |  | Yes | NGERP | KEEP | 2 | Sethu | Venkat |  | 07August2024 | 23August2024
15 | FORM | NTA NetOff Allocation | NTA NetOff Allocation | HQOW | C_Payment_V,C_Currency,UM_ATTRIBUTES,C_Bpartner,UM_GroupConfig,UM_WindowMapping,C_Invoice_v,UM_PartnerGroup | NTANetOffAllocationWindowImpl.java,NTANetOffAllocationWindow.java |  | Yes | NGERP | KEEP | 2 | Thinesh | Manjula |  | 07August2024
13 | FORM | NTA Payment Allocation AP | NTA Payment Allocation AP | HQOW | C_Payment_V,UM_ATTRIBUTES, c_invoice,c_currency,C_Bpartner,um_groupconfig,um_bpartnergroup | PaymentAllocationNTAAPWindowImpl.java, PaymentAllocationNTAAPWindow.java |  | Yes | NGERP | KEEP | 2 | Kishore | Manjula |  | 08August2024
14 | FORM | NTA Receipt Allocation | NTA Receipt Allocation | HQOW | C_Payment_V,C_Currency,C_Bpartner,UM_GroupConfig,UM_WindowMapping,C_Invoice_v,UM_PartnerGroup | NTAReceiptAllocationWindowImpl.java, NTAReceiptAllocationWindow.java |  | Yes | NGERP | KEEP | 2 | Kishore | Manjula |  | 08August2024
42 | FORM | Payment Allocation | Payment Allocation | ROW | C_Invoice_v,C_Currency,C_Payment_V | PaymentAllocationWindowImpl.java, PaymentAllocationWindow.java | C_Invoice_v,C_Payment_V | Yes | Compiere | MOVE | 16 | Kishore | KK |  | 05August2024 | 19August2024
43 | FORM | Payment Allocation - AP | Payment Allocation - AP | ROW | C_Invoice_v,C_Currency,C_Payment_V | PaymentAllocationAPWindowImpl.java, PaymentAllocationAPWindow.java | C_Invoice_v,C_Payment_V | Yes | NGERP | MOVE | 16 | Kishore | KK |  | 06August2024 | 20August2024
44 | FORM | Payment Allocation New | Payment Allocation New | ROW | C_Invoice_v,C_Currency,C_Payment_V | PaymentAllocationNewWindowImpl.java, PaymentAllocationNewWindow.java | C_Invoice_v,C_Payment_V | Yes | NGERP | MOVE | 16 | Kishore | KK |  | 06August2024 | 20August2024
45 | FORM | Payment Selection (manual) | Payment Selection (manual) | ROW | C_Invoice_v,C_Bpartner,C_Currency,C_PaymentTerm,C_PaySelectionLine,C_Bank,C_BankAccount | PaymentSelectionWindowImpl.java, PaymentSelectionWindow.java |  | Yes | Compiere | MOVE | 16 | Kishore | KK |  | 07August2024 | 22August2024
19 | FORM | price List version Tab, create pricelist | price List version Tab, create pricelist | HQOW | T_Selection,M_Product_PO,M_Product,M_DiscountSchemaLine, ad_org,M_PriceList_Version, M_PriceList | CreatePriceListWindowImpl.java |  | Yes | NGERP | KEEP | 2 | Imthiaz | Venkat |  | 07August2024 | 23August2024
46 | FORM | Print Batch DO | Print Batch DO | ROW | c_invoice,ad_org,c_doctype,m_inout,c_bpartner,c_bp_group, UM_CustomerProgram | PrintBatchDOwindowimpl.java |  | Yes | NGERP | MOVE | 16 | Thinesh | Hari |  | 06August2024 | 26August2024
47 | FORM | Print Batch Invoice | Print Batch Invoice | ROW | UM_PRINTINVOICE_V | PrintBatchInvoiceWindowImpl.java, PrintBatchInvoiceWindow.java | UM_PRINTINVOICE_V | Yes | NGERP | MOVE | 16 | Thinesh | Hari |  | 06August2024
4 | FORM | Print Batch NTA AR Invoice | Print Batch NTA AR Invoice | HQOW | C_Invoice,AD_Org,C_DocType, C_Bpartner,C_Order | PrintBatchInvoiceNTAARwindowImpl.java,PrintBatchInvoiceNTAARwindow.java |  | Yes | NGERP | KEEP | 2 | Sathish | Manirathnam |  | 07August2024 | 22August2024
18 | FORM | productInfo | productInfo | HQOW + ROW | M_PriceList,M_PriceList_Version,M_AttributeSetInstance,M_Locator,M_Warehouse,M_Product | InfoProductWindowImpl.java |  | No | Compiere | MERGE | 16 | Imthiaz | Manirathnam |  | 07August2024 | 23August2024
59 | FORM | ProductInfo-Trade | ProductInfo-Trade | HQOW + ROW | M_PriceList,M_PriceList_Version,M_AttributeSetInstance,M_Locator,M_Warehouse,M_Product | InfoProductWindowImpl.java |  | No | Compiere | MERGE | 16 | Selva | Venkat |  | 08August2024 | 23August2024 | Hari
48 | FORM | Re-Print System Receipt By Salesman | Re-Print System Receipt By Salesman | ROW | C_Payment,AD_User,C_Bpartner,UM_Bpartnergroup | RePrintCashReceiptBySalesmanWindowImpl.java, RePrintCashReceiptBySalesmanWindow.java |  | Yes | NGERP | MOVE | 16 | Thinesh | Hari |  | 05August2024 | 22August2024 | Hari
50 | FORM | Reject Approved Request | Reject Approved Request | ROW | UM_RequestLine,C_Bpartner | RejectApprovedReqWindowIml.java, RejectApprovedReqWindow.java |  | Yes | NGERP | MOVE | 16 | Yogan | Hari |  | 07August2024 |  | Hari
7 | FORM | Reject Commercial Discount | Reject Commercial Discount | HQOW | Um_Commdiscline,Um_Commdiscount,C_Campaign,c_bpartner | RejectApprovedCommDiscountWindowImpl.java,RejectApprovedCommDiscountWindow.java |  | Yes | NGERP | KEEP | 2 | Sethu | Hari |  | 05August2024 | 20August2024 | Hari
49 | FORM | RePrint Picking List Summary | RePrint Picking List Summary | ROW | M_Inout,M_InoutConfirm,C_Order,AD_User,M_Warehouse,C_Bpartner,C_Bpartner_Location,C_Location,C_BP_Group,C_Region,UM_Route,W_Rate | RePrintPickingListSummaryWindowImpl.java, RePrintPickingListSummaryWindow.java |  | Yes | NGERP | MOVE | 16 | Thinesh | Hari |  | 05August2024 | 22August2024 | Manirathnam
51 | FORM | System Cash Receipt By Salesman | System Cash Receipt By Salesman | ROW | C_Payment,AD_User,C_Bpartner,UM_Bpartnergroup | GenerateCashReceiptBySalesmanWindowImpl.java,GenerateCashReceiptBySalesmanWindow.java |  | Yes | NGERP | MOVE | 16 | Kishore | Hari |  | 09August2024 | 22August2024 | Manirathnam
52 | FORM | Update Customer Confirmation | Update Customer Confirmation | ROW | M_INOUTCONFIRM,AD_ORG,C_ORDER | UpdateCustomerConfirmationWindowImpl.java |  | Yes | NGERP | MOVE | 16 | Thinesh | Hari |  | 05August2024 |  | Manirathnam
53 | FORM | Update Invoice Details to TMS | Update Invoice Details to TMS | ROW | M_inout,c_order,c_doctype,ad_org,C_Bpartner,C_invoice | BatchInvoiceResendtoTMSWindowImpl.java |  | Yes | NGERP | MOVE | 16 | Imthiaz | Hari |  | 06August2024 |  | Manirathnam
16 | FORM | Update Is FAM Transaction | Update Is FAM Transaction | HQOW | GL_Journal,AD_ORG,C_Invoice | UpdateFAMTransactionsWindowImpl.java |  | Yes | NGERP | KEEP | 2 | Thinesh | Venkat |  | 07August2024 | 23August2024
54 | FORM | Update System ReceiptNo By Salesman | Update System ReceiptNo By Salesman | ROW | C_Payment,AD_User,C_Bpartner,UM_Bpartnergroup | UpdateSystemReceiptNoWindowImpl.java,UpdateSystemReceiptNoWindow.java |  | Yes | NGERP | MOVE | 16 | Jegan | Venkat |  | 06August2024 | 26August2024