## TPP123_29Jul-03Aug
# | SB | Service Request – Macro | Service Request – Micro | HQOW / ROW / FAM | Tables | Classes Used | SQL View Used | AD Impact | FITGAP (Compiere / NGERP) | 3R – KMM & MIW | Estimate | AssignedTo | QA | ADScript/CODE | DA Release Date | ReAssigned | QA Completion Date
1 | Purchase Management | AP Invoice | AP Invoice (Invoice (Vendor)) | HQOW + ROW | C_Invoice C_InvoiceLine C_InvoiceTax | Minvoice.java MinvoiceLine.java MinvoiceTax.java | NO | NO | Compiere | MERGE | 24 | Thinesh | Manirathnam |  | 02August2024 |  | 09August2024
2 | Sales Management | AR Extract Encryption | AR Extract Encryption | HQOW | X_UM_ARExtractEncrypt AD_Attachment | ARInvoiceExtract.java | UM_RV_ARINVOICEEXTRACT | NO | NGERP | KEEP | 2 | Imthiaz | Manirathnam |  | 25July2024 |  | 09August2024
3 | Sales Management | BUDGET | BUDGET | HQOW + ROW | UM_P2PBudget UM_SubBudget UM_BudgetProduct_Group | MP2PBudget.java MsubBudget.java MbudgetProductGroup.java | NO | NO | NGERP | MERGE | 4 | Imthiaz | Manirathnam |  | 25July2024 |  | 09August2024
4 | Sales Management | Cash Payment | Cash Payment | HQOW + ROW | C_Payment | Mpayment.java | NO | NO | Compiere | MERGE | 4 | Imthiaz | Manirathnam |  | 26July2024 |  | 09August2024
5 | Purchase Management | Clearance Account | Manage Clearing Account | HQOW | UM_Clearance | Mclearance.java | NO | NO | NGERP | KEEP | 4 | Imthiaz | Manirathnam |  | 25July2024 |  | 13August2024
6 | Purchase Management | Clearance Account | Post Clearing Account | HQOW | UM_Clearance | Mclearance.java Doc_Clearance.java | NO | NO | NGERP | KEEP | 4 | Imthiaz | Manirathnam |  | 26July2024 |  | 13August2024
7 | Purchase Management | COGS ADJUSTMENT FOR FIFO TO NET COST | COGS ADJUSTMENT FOR FIFO TO ONET COST | HQOW | UM_T_INVENTORYOUTADJDETAIL | COGSadjustmentFIFOtoNetcost.java | NO | NO | NGERP | KEEP | 4 | Imthiaz | Manirathnam |  | 29July2024 |  | 14August2024
8 | Sales Management | Commercial Discount | Manage Discount Conditions (Commercial Discount) | HQOW + ROW | UM_CommDiscount UM_CommDiscountLine | McommDiscount.java McommDiscLine.java | NO | NO | NGERP | MERGE | 4 | Imthiaz | Manirathnam |  | 26July2024 |  | 09August2024
9 | Sales Management | COMMERCIAL DISCOUNT APPROVAL | COMMERCIAL DISCOUNT APPROVAL | HQOW + ROW | UM_CommDiscount UM_CommDiscountLine | McommDiscount.java McommDiscLine.java | NO | NO | NGERP | MERGE | 4 | Imthiaz | Manirathnam |  | 30July2024 |  | 09August2024
10 | Purchase Management | CONTRACT NO | CONTRACT NO | HQOW + ROW | UM_ContractNo | McontractNo.java | NO | NO | NGERP | MERGE | 4 | Imthiaz | Manirathnam |  | 24July2024 |  | 16Aug2024
11 | Sales Management | CUSTOMER RETURN | CUSTOMER RETURN | HQOW + ROW | M_Inout M_InoutLine M_InoutConfirm M_InoutLineConfirm | Minout.java Minoutline.java | NO | NO | Compiere | MERGE | 12 | Sathish | Manirathnam |  | 01August2024 |  | 12August2024
12 | Sales Management | CUSTOMER RMA | CUSTOMER RMA | HQOW + ROW | C_Order C_OrderLine C_OrderTax | Morder.java MorderLine.java MorderTax.java | NO | NO | Compiere | MERGE | 12 | Sathish | Manirathnam |  | 01August2024 |  | 09August2024
13 | Sales Management | DO Confirm | DO Confirm | HQOW + ROW | M_Inout M_InoutLine M_InoutConfirm M_InoutLineConfirm | Minout.java Minoutline.java | NO | NO | Compiere | MERGE | 16 | Yogan | Manirathnam |  | 31July2024 |  | 16Aug2024
14 | Sales Management | DSO SALES ORDER APPROVAL | DSO SALES ORDER APPROVAL | HQOW + ROW | C_Order C_OrderLine C_OrderTax | Morder.java MorderLine.java MorderTax.java | NO | NO | NGERP | MERGE | 12 | Imthiaz | Manirathnam |  | 31July2024 |  | 16Aug2024
15 | Purchase Management | GOOD RECEIPT | GOOD RECEIPT | HQOW | C_Order C_OrderLine C_OrderTax | Morder.java MorderLine.java MorderTax.java | NO | NO | NGERP | KEEP | 24 | Sathish | Manirathnam |  | 01August2024 |  | 13August2024
16 | Purchase Management | MANAGE AP PAYMENT | MANAGE AP PAYMENT | HQOW + ROW | C_Payment | Mpayment.java | NO | NO | Compiere | MERGE | 8 | Sathish | Manirathnam |  | 29July2024 |  | 12August2024
17 | Sales Management | Manage Budget | Manage Budget | HQOW + ROW | UM_P2PBudget UM_SubBudget UM_BudgetProduct_Group | MP2PBudget.java MsubBudget.java MbudgetProductGroup.java | NO | NO | NGERP | MERGE | 4 | Sathish | Manirathnam |  | 29July2024 |  | 09August2024
18 | Purchase Management | Manage COGS Adjustment | Manage COGS Adjustment | HQOW + ROW | C_Invoice C_InvoiceLine C_InvoiceTax | Minvoice.java MinvoiceLine.java MinvoiceTax.java | NO | NO | NGERP | MERGE | 24 | Yogan | Manirathnam |  | 31July2024 |  | 09August2024
19 | Purchase Management | Manage COGS Adjustment (Posting) | Manage COGS Adjustment (Posting) | HQOW | C_Invoice C_InvoiceLine C_InvoiceTax Fact_Acct | Minvoice.java MinvoiceLine.java MinvoiceTax.java Doc_Invoice.java | NO | NO | NGERP | KEEP | 4 | Sathish | Manirathnam |  | 29July2024 |  | 13August2024
20 | Sales Management | Manage DO | Manage DO | HQOW + ROW | M_Inout M_InoutLine M_InoutConfirm M_InoutLineConfirm | Minout.java Minoutline.java | NO | NO | Compiere | MERGE | 24 | Thinesh | Manirathnam |  | 01August2024 |  | 16Aug2024
21 | Purchase Management | Manage Import Fee Data | Manage Import Fee Data | HQOW + ROW | UM_ImportFeeGroup Um_ImportFeeProductAlloc | MimportFeeGroup.java | NO | Ad_Process | NGERP | MERGE | 4 | Selva | Manirathnam |  | 30July2024 |  | 16Aug2024
22 | Sales Management | Manage Invoice | Manage Invoice | HQOW + ROW | C_Invoice C_InvoiceLine C_InvoiceTax | Minvoice.java MinvoiceLine.java MinvoiceTax.java | NO | NO | Compiere | MERGE | 24 | Krishna | Manirathnam |  | 01August2024 | Imthiaz | 12August2024
23 | Sales Management | Manage Invoice Approval | Manage Invoice Approval | HQOW + ROW | C_Invoice C_InvoiceLine C_InvoiceTax | Minvoice.java MinvoiceLine.java MinvoiceTax.java | NO | NO | NGERP | MERGE | 12 | Krishna | Manirathnam |  | 02August2024 | Imthiaz | 12August2024
24 | Purchase Management | Manage NTA AP Invoice | Manage NTA AP Invoice | HQOW + FAM | C_Invoice C_InvoiceLine C_InvoiceTax | Minvoice.java MinvoiceLine.java MinvoiceTax.java | NO | NO | NGERP | KEEP | 16 | Sathish | Manjula |  | 29July2024 |  | 16Aug2024
25 | Purchase Management | Manage NTA AP Payment | Manage NTA AP Payment | HQOW | C_Payment | Mpayment.java | NO | NO | NGERP | KEEP | 8 | Sathish | Manjula |  | 30July2024 |  | 16Aug2024
26 | Purchase Management | Manage NTA Receipt | Manage NTA Receipt | HQOW | C_Payment | Mpayment.java | NO | NO | NGERP | KEEP | 8 | Sathish | Manjula |  | 31July2024 |  | 16Aug2024
27 | Sales Management | Manage Promotion | Manage Promotion | HQOW | UM_Promotion C_Campaign UM_PromoCondition UM_PromoCombination | Mpromotion.java Mcampaign.java MpromoCondition.java MpromoCombination.java | NO | NO | NGERP | KEEP | 16 | Sathish | Manjula |  | 31July2024 |  | 16Aug2024
28 | Sales Management | MARKETING CAMPAIGN | MARKETING CAMPAIGN | HQOW + ROW | C_Campaign UM_CampaignMapping UM_MappingProvince UM_CampSubProposal UM_CampaignSKUAlloc UM_CampaignActivationLog | Mcampaign.java McampaignMapping.java McampSubProposal.java McampaignSKUAlloc.java InactivateCampaign.java | NO | NO | NGERP | MERGE | 12 | Jegan | Manjula |  | 01August2024 |  | 16Aug2024
29 | Purchase Management | MATERIAL RECEIPT | MATERIAL RECEIPT | HQOW + ROW | M_Inout M_InoutLine M_InoutConfirm M_InoutLineConfirm | Minout.java Minoutline.java | NO | NO | Compiere | MERGE | 16 | Sethu | Manjula |  | 02August2024 |  | 16Aug2024
30 | Purchase Management | Material Receipt Authorization | Material Receipt Authorization | HQOW + ROW | M_Inout M_InoutLine M_InoutConfirm M_InoutLineConfirm | Minout.java Minoutline.java | NO | NO | Compiere | MERGE | 12 | Sethu | Manjula |  | 02August2024
31 | Purchase Management | NTA AP Invoice | Create NTA AP Invoice without PO | HQOW | C_Invoice C_InvoiceLine C_InvoiceTax | Minvoice.java MinvoiceLine.java MinvoiceTax.java | NO | NO | NGERP | KEEP | 8 | Thinesh | Manjula |  | 24July2024 |  | 16Aug2024
32 | Purchase Management | NTA AP Invoice | Post Invoice | HQOW | C_Invoice C_InvoiceLine C_InvoiceTax | Minvoice.java MinvoiceLine.java MinvoiceTax.java | NO | NO | NGERP | KEEP | 2 | Jegan | Manjula |  | 24July2024 |  | 16Aug2024
33 | Purchase Management | NTA AP Invoice | Reject Invoice | HQOW | C_Invoice C_InvoiceLine C_InvoiceTax | Minvoice.java MinvoiceLine.java MinvoiceTax.java | NO | NO | NGERP | KEEP | 2 | Jegan | Manjula |  | 29July2024 |  | 16Aug2024
34 | Purchase Management | NTA AP Invoice | Validate Invoice Line | HQOW | C_Invoice C_InvoiceLine C_InvoiceTax | Minvoice.java MinvoiceLine.java MinvoiceTax.java | NO | NO | NGERP | KEEP | 2 | Jegan | KK |  | 29July2024 |  | 10August2024
35 | Purchase Management | NTA AP Invoice Confirmation | NTA AP Invoice Confirmation | HQOW | C_Invoice C_InvoiceLine C_InvoiceTax | Minvoice.java MinvoiceLine.java MinvoiceTax.java | NO | NO | NGERP | KEEP | 2 | Jegan | KK |  | 30July2024 |  | 10August2024
36 | Sales Management | NTA AR Invoice | Create NTA AR Invoice | HQOW | C_Invoice C_InvoiceLine C_InvoiceTax | Minvoice.java MinvoiceLine.java MinvoiceTax.java | NO | NO | NGERP | KEEP | 4 | Selva | KK |  | 29July2024 |  | 10August2024
37 | Sales Management | NTA AR Receipt | Manage NTA AR receipt | HQOW | C_Payment UM_Clearance | Mpayment.java | NO | NO | NGERP | KEEP | 4 | Selva | KK |  | 31July2024 |  | 10August2024
38 | Sales Management | NTA AR Receipt | Post AR receipt | HQOW | C_Payment Fact_Acct | Mpayment.java Doc_Payment.java | NO | NO | NGERP | KEEP | 4 | Jegan | KK |  | 01August2024 |  | 12August2024
39 | Sales Management | NTA Marketing Campaign | NTA Marketing Campaign | HQOW | C_Campaign UM_CampaignMapping UM_MappingProvince UM_CampSubProposal UM_CampaignSKUAlloc UM_CampaignActivationLog | Mcampaign.java McampaignMapping.java McampSubProposal.java McampaignSKUAlloc.java InactivateCampaign.java | NO | NO | NGERP | KEEP | 8 | Jegan | KK |  | 01August2024 |  | 13August2024
40 | Purchase Management | NTA Payment-AP | Complete AP Payment | HQOW | C_Payment | Mpayment.java | NO | NO | NGERP | KEEP | 8 | Jegan | KK |  | 02August2024 |  | 12August2024
41 | Purchase Management | NTA Payment-AP | Create AP Payment | HQOW | C_Payment | Mpayment.java | NO | NO | NGERP | KEEP | 2 | Jegan | Hari |  | 02August2024 |  | 09August2024
42 | Purchase Management | NTA Payment-AP | Post Payment | HQOW | C_Payment Fact_Acct | Mpayment.java Doc_Payment.java | NO | NO | NGERP | KEEP | 2 | Jegan | Hari |  | 02August2024 |  | 09August2024
43 | Purchase Management | NTA Purchase Order | Manage NTA Purchase Order | HQOW | C_Order C_OrderLine C_OrderTax | Morder.java MorderLine.java MorderTax.java | NO | NO | NGERP | KEEP | 2 | Jegan | Hari |  | 02August2024 |  | 09August2024
44 | Sales Management | Payment | Payment | HQOW + ROW | C_Payment | Mpayment.java | NO | NO | Compiere | MERGE | 8 | Selva | Manjula |  | 31July2024 |  | 16Aug2024
45 | Purchase Management | Payment - AP | Payment - AP | HQOW + ROW | C_Payment | Mpayment.java | NO | NO | NGERP | MERGE | 8 | Selva | Manjula |  | 31July2024 |  | 16Aug2024
46 | Sales Management | PAYMENT DETAILS | PAYMENT DETAILS | HQOW + ROW | C_Payment | Mpayment.java | NO | NO | NGERP | MERGE | 8 | Selva | Manjula |  | 31July2024 |  | 16Aug2024
47 | Purchase Management | Payment Netoff | Post Net-Off Payment | HQOW | C_Payment Fact_Acct | Doc_Payment.java Mpayment.java | NO | NO | NGERP | KEEP | 2 | Thinesh | Hari |  | 24July2024 |  | 09August2024
48 | Sales Management | Proposal SKU | Proposal SKU | HQOW | UM_ProposalSKU I_ProposalSKU | MproposalSKU.java | NO | NO | NGERP | KEEP | 8 | Selva | Hari |  | 01August2024 |  | 09August2024
49 | Purchase Management | Purchase Order | Purchase Order | HQOW + ROW | C_Order C_OrderLine C_OrderTax | Morder.java MorderLine.java MorderTax.java | NO | NO | Compiere | MERGE | 8 | Thinesh | Manjula |  | 29July2024 |  | 16Aug2024
50 | Purchase Management | Rejection Code | Define Rejection Code | HQOW + ROW | UM_RejectionCode | X_UM_RejectionCode.java | NO | NO | NGERP | MERGE | 4 | Selva | Manjula |  | 31July2024 |  | 16Aug2024
51 | Purchase Management | Return to Vendor | Return to Vendor | HQOW + ROW | M_Inout M_InoutLine M_InoutConfirm M_InoutLineConfirm | Minout.java Minoutline.java | NO | NO | Compiere | MERGE | 8 | Selva | Manjula |  | 31July2024
52 | Sales Management | Sales Order | Sales Order | HQOW + ROW | C_Order C_OrderLine C_OrderTax | Morder.java MorderLine.java MorderTax.java | NO | NO | Compiere | MERGE | 16 | Krishna | Manjula |  | 01August2024 |  | 16Aug2024
53 | Sales Management | Super Payment | Super Payment | HQOW + ROW | C_Payment | Mpayment.java | NO | NO | NGERP | MERGE | 4 | Selva | Manjula |  | 31July2024 |  | 16Aug2024
54 | Purchase Management | Treasury File Encryption | Treasury File Encryption | HQOW | UM_TreasuryFileEncrypt AD_Attachment GL_JOURNAL | GenerateTreasuryEncryptionWindowImpl.java | NO | NO | NGERP | KEEP | 4 | Selva | Hari |  | 01August2024 |  | 12August2024
55 | Purchase Management | VAT Transfer (NTA) | Complete VAT Transfer – Update invoice | HQOW | UM_VATTransfer | MvatTransfer.java | NO | NO | NGERP | KEEP | 4 | Selva | Hari |  | 01August2024 |  | 12August2024
56 | Purchase Management | VAT Transfer (NTA) | Manage VAT Transfer (write off / declared/Undeclared) | HQOW | UM_VATTransfer | MvatTransfer.java | NO | NO | NGERP | KEEP | 4 | Sethu | Venkat |  | 29July2024 |  | 13August2024
57 | Purchase Management | VAT Transfer | Post VAT Transfer | HQOW | UM_VATTransfer Fact_Acct | Doc_VATTransfer.java MvatTransfer.java | NO | NO | NGERP | MERGE | 4 | Sethu | Venkat |  | 29July2024 |  | 13August2024
58 | Purchase Management | VAT Transfer | VAT Net Off | HQOW | UM_VATTransfer | MvatTransfer.java | NO | NO | NGERP | MERGE | 2 | Sethu | Venkat |  | 31July2024 |  | 13August2024
59 | Purchase Management | VAT Transfer | VAT Replenishment | HQOW | UM_VATTransfer | MvatTransfer.java | NO | NO | NGERP | MERGE | 2 | Sethu | Venkat |  | 01August2024 |  | 13August2024
60 | Purchase Management | VAT Transfer(Trade) | Manage Transfer - Update Invoice | HQOW + ROW | UM_VATTransfer | MvatTransfer.java | NO | NO | NGERP | MERGE | 4 | Sethu | Manjula |  | 01August2024 |  | 16Aug2024
61 | Purchase Management | VAT Transfer(Trade) | Create Transfer | HQOW + ROW | UM_VATTransfer | MultiVatTransferWindowImpl.java | NO | NO | NGERP | MERGE | 4 | Sethu | Manjula |  | 02August2024 |  | 16Aug2024
62 | Purchase Management | Vendor RMA | Vendor RMA | HQOW + ROW | C_Order C_OrderLine C_OrderTax | Morder.java MorderLine.java MorderTax.java | NO | NO | Compiere | MERGE | 16 | Sathish | Manjula |  | 02August2024 |  | 16Aug2024
63 | Sales Management | View Allocation | View Allocation | HQOW + ROW | C_AllocationHDR C_AllocationLine | MallocationHDR.java MallocationLine.java | NO | NO | Compiere | MERGE | 4 | Sethu | Manjula |  | 30July2024 |  | 16Aug2024
64 | Inventory Management | Consignment Order | Consignment Order | HQOW + ROW | UM_ConsignmentOrder UM_ConsignmentOrderLine | MconsignmentOrder.java MconsignmentOrderLine.java | NO | NO | NGERP | MERGE | 16 | Sethu | Manjula |  | 31July2024 |  | 16Aug2024
65 | Inventory Management | Internal Move Confirmation | Internal Move Confirmation | HQOW + ROW | M_MovementConfirm M_MovementLineConfirm | MmovementConfirm.java MmovementLineConfirm.java | NO | NO | NGERP | MERGE | 8 | Sethu | Manjula |  | 02August2024 |  | 16Aug2024
66 | Inventory Management | Internal Transfer | Export XML file for printing internal transfer | ROW | C_Invoice C_Bpartner C_Order C_Bp_BankAccount C_Doctype UM_RejectionCode | GenerateEInvoiceXML.java InvoiceHeaderforXML.java InvoiceLineforXML.java | NO | Ad_Process | NGERP | MOVE | 24 | Sethu | KK |  | 02August2024 |  | 13August2024
67 | Inventory Management | INTERNAL TRANSFER GIFT | INTERNAL TRANSFER GIFT | HQOW + ROW | M_movement M_MovementLine | Mmovement.java MmovementLine.java | NO | NO | NGERP | MERGE | 24 | Yogan | KK |  | 31July2024 |  | 13August2024
68 | Inventory Management | INTERNAL TRANSFER INVOICE | INTERNAL TRANSFER INVOICE | HQOW + ROW | C_Invoice C_InvoiceLine C_InvoiceTax C_InvoicePaySchedule | Minvoice.java MinvoiceLine.java MinvoiceTax.java MinvoicePaySchedule.java | NO | NO | NGERP | MERGE | 8 | Sridhar | KK |  | 01August2024 |  | 13August2024
69 | Inventory Management | Manage Import Product Fee Alloc | Manage Import Product Fee Alloc | HQOW | UM_ImportFeeGroup Um_ImportFeeProductAlloc | MimportFeeGroup.java ValidateImportFeeGroup.java | NO | NO | NGERP | KEEP | 8 | Sridhar | Venkat |  | 01August2024 |  | 20August2024
70 | Inventory Management | Manage Physical Inventory Gift | Manage Physical Inventory Gift | HQOW + ROW | M_Inventory M_InventoryLine M_InventoryLineMA | Minventory.java MinventoryLine.java MinventoryLineMA.java | NO | NO | Compiere | MERGE | 8 | Sridhar | KK |  | 31July2024 |  | 12August2024
71 | Inventory Management | MANAGE TALLYSHEET | MANAGE TALLYSHEET | HQOW + ROW | M_Inout M_InoutLine | MInout.java Minoutline.java | NO | NO | NGERP | MERGE | 12 | Imthiaz | KK |  | 25July2024 |  | 12August2024
72 | Inventory Management | MANAGE TALLYSHEET CONFIRMATION | MANAGE TALLYSHEET CONFIRMATION | HQOW + ROW | M_Inout M_InoutLine | MInout.java Minoutline.java | NO | NO | NGERP | MERGE | 4 | Sridhar | KK |  | 25July2024 |  | 12August2024
73 | Inventory Management | Metro Transfer | Metro Transfer | HQOW + ROW | M_Movement M_MovementLine M_MovementLIneMA | MMovement.java MmovementLine.java MmovementLineMA.java | NO | NO | NGERP | MERGE | 4 | Sridhar | KK |  | 25July2024 |  | 14August2024
74 | Inventory Management | Move Confirmation (VAS,Metro,Borrow) | Move Confirmation (VAS,Metro,Borrow) | HQOW + ROW | M_MovementConfirm M_MovementLineConfirm | MMovementConfirm.java MmovementLineConfirm.java | NO | NO | NGERP | MERGE | 8 | Sridhar | KK |  | 01August2024 |  | 14August2024
75 | Inventory Management | Physical Inventory | Physical Inventory | HQOW + ROW | M_Inventory M_InventoryLine M_InventoryLineMA | Minventory.java MinventoryLine.java MinventoryLIneMA.java | NO | NO | Compiere | MERGE | 16 | Jegan | KK |  | 30July2024 |  | 14August2024
76 | Inventory Management | Physical Inventory Authorization | Physical Inventory Authorization | HQOW + ROW | M_Inventory M_InventoryLine M_InventoryLineMA | Minventory.java MinventoryLine.java MinventoryLIneMA.java | NO | NO | NGERP | MERGE | 8 | Jegan | KK |  | 31July2024 |  | 14August2024
77 | Inventory Management | Production | Production | HQOW + ROW | M_Production M_ProductionPlan M_ProductionLine | Mproduction.java MproductionPlan.java MproductionLine.java MproductionLineMA.java | NO | NO | Compiere | MERGE | 24 | Krishna | KK |  | 01August2024 | Imthiaz | 14August2024
78 | Inventory Management | Production Setup | Production Setup | HQOW + ROW | M_Production M_ProductionPlan M_ProductionLine Ad_Role | Mproduction.java MproductionPlan.java MproductionLine.java MproductionLineMA.java Mrole.java ProductionRun.java | NO | NO | Compiere | MERGE | 12 | Krishna | KK |  | 01August2024 | Imthiaz | 14August2024
79 | Inventory Management | Receiving Branch Transfer | Receiving Branch Transfer | HQOW + ROW | M_Movement M_MovementLine M_MovementLineMA AD_Attachment | MMovement.java MmovementLine.java MmovementLineMA.java Mattachment.java | NO | NO | NGERP | MERGE | 16 | Sridhar | KK |  | 02August2024 |  | 23August2024
80 | Inventory Management | Receiving Branch Transfer – Gift | Receiving Branch Transfer – Gift | HQOW + ROW | M_Movement M_MovementLine M_MovementLineMA AD_Attachment | MMovement.java MmovementLine.java MmovementLineMA.java Mattachment.java | NO | NO | NGERP | MERGE | 8 | Sridhar | KK |  | 02August2024 |  | 23August2024
81 | Inventory Management | Sending Branch Transfer | Sending Branch Transfer | HQOW + ROW | M_Movement M_MovementLine M_MovementLineMA AD_Attachment | MMovement.java MmovementLine.java MmovementLineMA.java Mattachment.java | NO | NO | NGERP | MERGE | 16 | Sridhar | Hari |  | 02August2024 |  | 13August2024
82 | Inventory Management | Sending Branch Transfer – Gift | Sending Branch Transfer – Gift | HQOW + ROW | M_Movement M_MovementLine M_MovementLineMA AD_Attachment | MMovement.java MmovementLine.java MmovementLineMA.java Mattachment.java | NO | NO | NGERP | MERGE | 8 | Sridhar | KK |  | 02August2024 |  | 23August2024
83 | Inventory Management | Stock take adjustment | Stock take adjustment | HQOW + ROW | M_Inventory M_InventoryLine M_InventoryLineMA | Minventory.java MinventoryLine.java MinventoryLineMA.java | NO | NO | NGERP | MERGE | 8 | Sridhar | Hari |  | 30July2024 |  | 12August2024
84 | Inventory Management | Stock take adjustment authorization | Stock take adjustment authorization | HQOW + ROW | M_Inventory M_InventoryLine M_InventoryLineMA | Minventory.java MinventoryLine.java MinventoryLIneMA.java | NO | NO | NGERP | MERGE | 8 | Sridhar | Hari |  | 30July2024 |  | 12August2024
85 | FAM Management | Manage CIP Register | CIP Register | HQOW + FAM | UM_CIPRegister | MCIPRegister.java | NO | NO | NGERP | MERGE | 4 | Yogan | Hari |  | 29July2024 |  | 12August2024
86 | FAM Management | Posting CIP Transfer | Posting CIP Transfer | HQOW + FAM | Fact_Acct | Doc_TransferCIP.java | NO | NO | NGERP | MERGE | 4 | Yogan | Hari |  | 31July2024 |  | 12August2024
87 | FAM Management | Manage FA Register | Manage FA Register | HQOW + FAM | UM_FARegister, UM_FARegisterLine | MFARegister.java MFARegisterLine.java | NO | NO | NGERP | MERGE | 4 | Yogan | Hari |  | 30July2024 |  | 13August2024
88 | FAM Management | FA Disposal & Write Off | FA Disposal & Write Off | HQOW + FAM | UM_FADisposalWriteoff, UM_FADisposalWriteoffLine | MFADisposalWriteoff.java MFADisposalWriteoffLine.java | NO | NO | NGERP | MERGE | 4 | Yogan | Hari |  | 01August2024 |  | 13August2024
89 | FAM Management | Depreciation GL Mapping | Depreciation GL Mapping | HQOW + FAM |  |  |  |  | NGERP | MERGE | 4 | Yogan | Hari |  | 31July2024 |  | 13August2024
90 | FAM Management | Create GL Journal | GL Journal | HQOW + FAM | GL_Journal, GL_JournalLine | Mjournal.java MjournalLine.java | NO | NO | Compiere | MERGE | 8 | Yogan | Hari |  | 31July2024 |  | 16Aug2024
91 | FAM Management | GL Journal Authorization | GL Journal Authorization | HQOW + FAM | GL_Journal, GL_JournalLine | Mjournal.java MjournalLine.java | NO | NO | Compiere | MERGE | 8 | Yogan | Hari |  | 31July2024 |  | 16Aug2024
92 | FAM Management | Auto Booking FA Disposal & Write Off | Auto Booking FA Disposal | FAM |  |  |  |  | NGERP | MOVE | 4 | Yogan | Hari |  | 31July2024 |  | 16Aug2024
93 | FAM Management | FA Depreciation monthly | FA Depreciation monthly | FAM | UM_FARegister, UM_FARegisterLine | DepreciationProcess.java | NO | NO | NGERP | MOVE | 4 | Kishore | Hari |  | 02August2024 |  | 16Aug2024
94 | Purchase Management | AP Payment | AP Payment | HQOW + ROW | C_Payment | Mpayment.java | NO | NO | NGERP | MERGE | 4 | Kishore | Hari |  | 02August2024 |  | 13August2024
95 | Sales Management | Customer Return | Customer Exchange (Same Price) | HQOW + ROW | M_Inout M_InoutLine | MInout.java Minoutline.java | NO | NO | Compiere | MERGE | 8 | Kishore | Hari |  | 02August2024 |  | 14August2024
96 | Sales Management | Customer Return | Customer Exchange (different price) | HQOW + ROW | M_Inout M_InoutLine | MInout.java Minoutline.java | NO | NO | Compiere | MERGE | 8 | Kishore | Hari |  | 02August2024 |  | 14August2024
97 | Sales Management | Customer RMA Authorization | Customer RMA Authorization | HQOW + ROW | C_Order C_OrderLine C_OrderTax | MOrder.java MorderLine.java MorderTax.java | NO | NO | NGERP | MERGE | 8 | Kishore | Hari |  | 02August2024 |  | 14August2024
98 | Sales Management | Manage Attribute Combinations | Manage Attribute Combinations | ROW | UM_PromoCombionation | X_UM_PromoCombination.java | NO | NO | NGERP | MOVE | 4 | Kishore | Hari |  | 02August2024 |  | 16Aug2024
99 | Sales Management | Manage SO Campaigns | Manage SO Multi Campaigns | ROW | I_SoCampaign UM_SoCampaign | NO | NO | NO | NGERP | MOVE | 8 | Kishore | Hari |  | 01August2024 |  | 16Aug2024
100 | Inventory Management | Manage Transport Manifest | Manage Transport Manifest | ROW | UM_ManiFest UM_ManiFestLine | MmaniFest.java MmaniFestLine.java | NO | NO | NGERP | MOVE | 8 | Kishore | Venkat |  | 30July2024 |  | 13August2024
101 | Inventory Management | MEMO: Short Dated Inventory Control – Scheduler | MEMO: Short Dated Inventory Control | ROW | Ad_Scheduler Ad_SchedulerPara Ad_SchedulerLog T_ShortDatedInventory | ShortDatedInventory.java | NO | NO | NGERP | MOVE | 8 | Kishore | Venkat |  | 30July2024 |  | 21August2024
102 | Sales Management | Order delivery Plan Report - Process | Order delivery Plan Report – Process | ROW | C_Invoice C_InvoiceLine M_Inout M_InoutLine M_Product M_AttributeSetInstance C_Order M_Locator | OrderDeliveryPlanReport.java | NO | NO | NGERP | MOVE | 8 | Kishore | Venkat |  | 01August2024 |  | 14August2024
103 | Inventory Management | Physical Inventory Authorization Gift | Physical Inventory Authorization Gift | HQOW + ROW | M_Inventory M_InventoryLine M_InventoryLineMA | MInventory.java MinventoryLine.java MinventoryLineMA.java | NO | NO | NGERP | MERGE | 8 | Kishore | Venkat |  | 01August2024 |  | 13August2024
104 | Sales Management | Print Batch DO | Manage DO Ticked check Box | ROW | M_inout C_Doctype C_Bpartner C_Bp_Group | PrintBatchDoWindowImpl.java ReportCtl.java | NO | NO | NGERP | MOVE | 8 | Thinesh | Venkat |  | 02August2024 |  | 14August2024
105 | Sales Management | Print Batch invoice CDI | Print Batch invoice CDI | ROW | C_Invoice C_InvoiceLine | PrintBatchInvoiceWindowImpl.java PrintBatchInvoiceWindow.java GenerateEInvoiceXML.java | NO | NO | NGERP | MOVE | 4 | Thinesh | Venkat |  | 02August2024 |  | 14August2024
106 | Sales Management | Receivables Write Off | Write Off | HQOW | C_AllocationHDR C_AllocationLine |  |  |  | NGERP | KEEP | 2 | Thinesh | Venkat |  | 26July2024 | Hari | 19August2024
107 | Sales Management | Sales Order | Consignment Type Order | HQOW + ROW | C_Order UM_ConsignmentOrder UM_ConsignmentOrderLine.java | Morder.java MconsignmentOrder.java MconsignmentOrderLine.java | NO | NO | NGERP | MERGE | 8 | Thinesh | Venkat |  | 01August2024 |  | 21August2024
108 | Sales Management | Sales Order | Process Sales Order | ROW | C_Order C_OrderLine C_OrderTax | Morder.java MorderLine.java MorderTax.java | NO | NO | Compiere | MOVE | 8 | Thinesh | Venkat |  | 01August2024 |  | 21August2024
109 | Sales Management | Sales Order | Promotion Order | HQOW + ROW | C_Order C_OrderLine C_OrderTax | Morder.java MorderLine.java MorderTax.java | NO | NO | NGERP | MERGE | 8 | Thinesh | Venkat |  | 31July2024 |  | 14August2024
110 | Sales Management | Sales Order | SG&A Non Register Order | HQOW + ROW | C_Order C_OrderLine C_OrderTax | Morder.java MorderLine.java MorderTax.java | NO | NO | NGERP | MERGE | 8 | Thinesh | Venkat |  | 31July2024 |  | 09August2024
111 | Sales Management | Sales Order | SG&A Register Order | HQOW + ROW | C_Order C_OrderLine C_OrderTax | Morder.java MorderLine.java MorderTax.java | NO | NO | NGERP | MERGE | 8 | Thinesh | Venkat |  | 30July2024 |  | 09August2024
112 | Sales Management | Sales Order | Topline Non Register Order | HQOW + ROW | C_Order C_OrderLine C_OrderTax | Morder.java MorderLine.java MorderTax.java | NO | NO | NGERP | MERGE | 8 | Krishna | Venkat |  | 01August2024 |  | 09August2024
113 | Sales Management | Sales Order | Topline Register Order | HQOW + ROW | C_Order C_OrderLine C_OrderTax | Morder.java MorderLine.java MorderTax.java | NO | NO | NGERP | MERGE | 8 | Krishna | Venkat |  | 01August2024 |  | 09August2024
114 | Sales Management | Sales Order | Consignment of Promotion Order (delivery fee) | HQOW + ROW | C_Order C_OrderLine C_OrderTax | Morder.java MorderLine.java MorderTax.java | NO | NO | NGERP | MERGE | 8 | Selva | Venkat |  | 02August2024
115 | Inventory Management | Synch-in-Transit | Synch-in-Transit | ROW | M_Movement M_MovementLine M_MovementLineMA M_AttributeSetInstance M_Inventory M_InventoryLine | SynchronizeTransfer.java | NO | NO | NGERP | MOVE | 24 | Krishna | Venkat |  | 01August2024 | Hari | 19August2024
116 | Inventory Management | UnPack Package | Unpack Package | ROW | M_Production M_ProductionPlan M_ProductionLine | UnPackPackages.java | NO | NO | NGERP | MOVE | 16 | Yogan | Venkat |  | 02August2024 | Hari | 19August2024
117 | Sales Management | Validate Import Proposal SKU | Validate Import Proposal SKU | HQOW |  |  |  | NO | NGERP | KEEP | 2 | Krishna | Venkat |  | 01August2024 | Hari | 19August2024
118 | Sales Management | P2P Sku Contribution | Manage Contribution Topline Sub proposal Ratio | HQOW |  |  |  | NO | NGERP | KEEP | 2 | Krishna | Manirathnam |  | 01August2024 |  | 12August2024
119 | Sales Management | GAAP TOPLINE NTA RATIO REPORT | GAAP TOPLINE NTA RATIO REPORT | HQOW | c_period,C_YEAR,UM_T_GAAPTOPLINENTARATIORPT,m_product,m_product_category,um_t_grosstlntaratio_mix, Um_proposalmaster,UM_T_GROSSTLNTARATIO,UM_SKUContributionPerc,um_proposalsku, | MasterGAAPToplineNTARatioReportNew.java |  | NO | NGERP | KEEP | 2 | Krishna | Manjula |  | 02August2024 |  | 16Aug2024
120 | Sales Management | Cash Payment | Manage Cash Payment | ROW |  |  |  | YES | NGERP | MOVE | 4 | Krishna | Venkat |  | 02August2024 | Imthiaz | 13August2024
121 | Purchase Management | COGS Adjustment | COGS Adjustment | HQOW |  |  |  | NO | NGERP | KEEP | 12 | Kishore | Hari |  | 31July2024 |  | 14August2024
122 | Sales Management | Manage Invoice | Invoice Tax | ROW | c_invoicetax,c_invoice,c_doctype,c_bpartner |  | RV_C_InvoiceTax | NO | Compiere | MOVE | 4 | Krishna | Venkat |  | 02August2024 | Imthiaz | 13August2024
123 | Sales Management | Expense Report | Expense Report | HQOW | c_bpartner,c_invoice,c_allocationline,c_allocationhdr,c_invoice,c_invoiceline,m_inoutline,m_inout,C_BP_BankAccount | ExportAPCitiReport.java |  | NO | NGERP | KEEP | 2 | Sridhar | Venkat |  | 30July2024 |  | 13August2024