## TPP
# | SERVICE BUNDLES | SERVICE REQUEST -MACRO | SERVICE REQUEST -MICRO | HQ/ROW | Invalid SR | VERIFY CREATE | VERIFY UPDATE | VERIFY DELETE | VERIFY COMPLETE | VERIFY FIELD | VERIFY POSTING | VERIFY SCREEN PRINT | VERIFY VOID/REVERSE | VERIFY REVERSE DOCUMENT/ POSTING | Document Sequence (Before) | Document Sequence (After) | OVERALL STATUS | COMMENT | TEST DATA | TESTED BY | QA APPROVED BY | QA TIME | TICKET ID | START DATE | END DATE
1 | Purchase Management | AP Invoice | AP Invoice (Invoice (Vendor) | HQOW + ROW | [15 empty] | Santhosh
2 | Sales Management | AR Extract Encryption | AR Extract Encryption | HQOW
3 | Sales Management | BUDGET | BUDGET | HQOW + ROW
4 | Sales Management | Cash Payment | Cash Payment | HQOW + ROW
5 | Purchase Management | Clearance Account | Manage Clearing Account | HQOW
6 | Purchase Management | Clearance Account | Post Clearing Account | HQOW
7 | Purchase Management | COGS ADJUSTMENT FOR FIFO TO NET COST | COGS ADJUSTMENT FOR FIFO TO ONET COST | HQOW
8 | Sales Management | Commercial Discount | Manage Discount Conditions (Commercial Discount) | HQOW + ROW
9 | Sales Management | COMMERCIAL DISCOUNT APPROVAL | COMMERCIAL DISCOUNT APPROVAL | HQOW + ROW
10 | Purchase Management | CONTRACT NO | CONTRACT NO | HQOW + ROW | [15 empty] | Santhosh
11 | Sales Management | CUSTOMER RETURN | CUSTOMER RETURN | HQOW + ROW
12 | Sales Management | CUSTOMER RMA | CUSTOMER RMA | HQOW + ROW
13 | Sales Management | DO Confirm | DO Confirm | HQOW + ROW
14 | Sales Management | DSO SALES ORDER APPROVAL | DSO SALES ORDER APPROVAL | HQOW + ROW
15 | Purchase Management | GOOD RECEIPT | GOOD RECEIPT | HQOW |  | Pass | Pass | Pass | Pass | Pass | 0 | Pass | Pass |  | 1NGR2411-10301 | 1NGR2501-10003 | Fail | Date Ordered field is not editable after completing the document Centra. But it should be editable |  | Santhosh
16 | Purchase Management | MANAGE AP PAYMENT | MANAGE AP PAYMENT | HQOW + ROW | [15 empty] | Santhosh
17 | Sales Management | Manage Budget | Manage Budget | HQOW + ROW
18 | Purchase Management | Manage COGS Adjustment | Manage COGS Adjustment | HQOW + ROW
19 | Purchase Management | Manage COGS Adjustment (Posting) | Manage COGS Adjustment (Posting) | HQOW
20 | Sales Management | Manage DO | Manage DO | HQOW + ROW
21 | Purchase Management | Manage Import Fee Data | Manage Import Fee Data | HQOW + ROW
22 | Sales Management | Manage Invoice | Manage Invoice | HQOW + ROW
23 | Sales Management | Manage Invoice Approval | Manage Invoice Approval | HQOW + ROW
24 | Purchase Management | Manage NTA AP Invoice | Manage NTA AP Invoice | HQOW + FAM | [15 empty] | Santhosh
25 | Purchase Management | Manage NTA AP Payment | Manage NTA AP Payment | HQOW | [15 empty] | Santhosh
26 | Purchase Management | Manage NTA Receipt | Manage NTA Receipt | HQOW | [15 empty] | Santhosh
27 | Sales Management | Manage Promotion | Manage Promotion | HQOW
28 | Sales Management | MARKETING CAMPAIGN | MARKETING CAMPAIGN | HQOW + ROW
29 | Purchase Management | MATERIAL RECEIPT | MATERIAL RECEIPT | HQOW + ROW | [15 empty] | Santhosh
30 | Purchase Management | Material Receipt Authorization | Material Receipt Authorization | HQOW + ROW | [15 empty] | Santhosh
31 | Purchase Management | NTA AP Invoice | Create NTA AP Invoice without PO | HQOW |  | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | 1NAP2501-10105 | 1NAP2501-10105 | Fail | Trade Marketing Campaign is loading in NTA AP INVOICE LINE | 1NAP2501-10105 | Santhosh
32 | Purchase Management | NTA AP Invoice | Post Invoice | HQOW | [15 empty] | Santhosh
33 | Purchase Management | NTA AP Invoice | Reject Invoice | HQOW | [15 empty] | Santhosh
34 | Purchase Management | NTA AP Invoice | Validate Invoice Line | HQOW | [15 empty] | Santhosh
35 | Purchase Management | NTA AP Invoice Confirmation | NTA AP Invoice Confirmation | HQOW | [15 empty] | Santhosh
36 | Sales Management | NTA AR Invoice | Create NTA AR Invoice | HQOW
37 | Sales Management | NTA AR Receipt | Manage NTA AR receipt | HQOW
38 | Sales Management | NTA AR Receipt | Post AR receipt | HQOW
39 | Sales Management | NTA Marketing Campaign | NTA Marketing Campaign | HQOW
40 | Purchase Management | NTA Payment-AP | Complete AP Payment | HQOW |  | Pass | Pass | Pass | Pass | Fail | Pass | Pass | Pass | Pass | 79654001A02411-1022 | 79654001A12501-10002 | Fail | Department field in NTA AP Paymentis not showing in centra HQ but showing in HQOW |  | Santhosh
41 | Purchase Management | NTA Payment-AP | Create AP Payment | HQOW | [15 empty] | Santhosh
42 | Purchase Management | NTA Payment-AP | Post Payment | HQOW | [15 empty] | Santhosh
43 | Purchase Management | NTA Purchase Order | Manage NTA Purchase Order | HQOW |  | Pass | Pass | Pass | Pass | Pass | 0 | Pass | Pass |  | 1NPO2411-10802 | 1NPO2412-10107 | Fail | Order line allows to Trade marketing Campaign. But it should not allow | 1NPO2412-10107 | Santhosh
44 | Sales Management | Payment | Payment | HQOW + ROW
45 | Purchase Management | Payment - AP | Payment - AP | HQOW + ROW | [15 empty] | Santhosh
46 | Sales Management | PAYMENT DETAILS | PAYMENT DETAILS | HQOW + ROW
47 | Purchase Management | Payment Netoff | Post Net-Off Payment | HQOW | [15 empty] | Santhosh
48 | Sales Management | Proposal SKU | Proposal SKU | HQOW
49 | Purchase Management | Purchase Order | Purchase Order | HQOW + ROW |  | Pass | Pass | Pass | Pass | Pass | 0 | Fail | Pass |  | 1PO2411-10016 | 1PO2412-10061 | Fail | Extra tele no Column in Print in po print formate PO_DenEast_Version2 C_Order_Header_v2 print formate is showing in 8182 but not showing in Centra HQ | Abbott: 1PO2412-10061 DenEast: 1PO2412-10064 | Santhosh
50 | Purchase Management | Rejection Code | Define Rejection Code | HQOW + ROW | [15 empty] | Santhosh
51 | Purchase Management | Return to Vendor | Return to Vendor | HQOW + ROW | [15 empty] | Santhosh
52 | Sales Management | Sales Order | Sales Order | HQOW + ROW
53 | Sales Management | Super Payment | Super Payment | HQOW + ROW
54 | Purchase Management | Treasury File Encryption | Treasury File Encryption | HQOW
55 | Purchase Management | VAT Transfer (NTA) | Complete VAT Transfer – Update invoice | HQOW
56 | Purchase Management | VAT Transfer (NTA) | Manage VAT Transfer (write off / declared/Undeclared) | HQOW
57 | Purchase Management | VAT Transfer | Post VAT Transfer | HQOW
58 | Purchase Management | VAT Transfer | VAT Net Off | HQOW
59 | Purchase Management | VAT Transfer | VAT Replenishment | HQOW
60 | Purchase Management | VAT Transfer(Trade) | Manage Transfer - Update Invoice | HQOW + ROW
61 | Purchase Management | VAT Transfer(Trade) | Create Transfer | HQOW + ROW
62 | Purchase Management | Vendor RMA | Vendor RMA | HQOW + ROW | [15 empty] | Santhosh
63 | Sales Management | View Allocation | View Allocation | HQOW + ROW
64 | Inventory Management | Consignment Order | Consignment Order | HQOW + ROW | [15 empty] | KK
65 | Inventory Management | Internal Move Confirmation | Internal Move Confirmation | HQOW + ROW | [15 empty] | KK
66 | Inventory Management | Internal Transfer | Export XML file for printing internal transfer | ROW | [15 empty] | KK
67 | Inventory Management | INTERNAL TRANSFER GIFT | INTERNAL TRANSFER GIFT | HQOW + ROW | [15 empty] | KK
68 | Inventory Management | INTERNAL TRANSFER INVOICE | INTERNAL TRANSFER INVOICE | HQOW + ROW | [15 empty] | KK
69 | Inventory Management | Manage Import Product Fee Alloc | Manage Import Product Fee Alloc | HQOW
70 | Inventory Management | Manage Physical Inventory Gift | Manage Physical Inventory Gift | HQOW + ROW | [15 empty] | KK
71 | Inventory Management | MANAGE TALLYSHEET | MANAGE TALLYSHEET | HQOW + ROW | [15 empty] | KK
72 | Inventory Management | MANAGE TALLYSHEET CONFIRMATION | MANAGE TALLYSHEET CONFIRMATION | HQOW + ROW | [15 empty] | KK
73 | Inventory Management | Metro Transfer | Metro Transfer | HQOW + ROW
74 | Inventory Management | Move Confirmation (VAS,Metro,Borrow) | Move Confirmation (VAS,Metro,Borrow) | HQOW + ROW | [15 empty] | KK
75 | Inventory Management | Physical Inventory | Physical Inventory | HQOW + ROW | [15 empty] | KK
76 | Inventory Management | Physical Inventory Authorization | Physical Inventory Authorization | HQOW + ROW | [15 empty] | KK
77 | Inventory Management | Production | Production | HQOW + ROW | [15 empty] | KK
78 | Inventory Management | Production Setup | Production Setup | HQOW + ROW | [15 empty] | KK
79 | Inventory Management | Receiving Branch Transfer | Receiving Branch Transfer | HQOW + ROW | [15 empty] | KK
80 | Inventory Management | Receiving Branch Transfer – Gift | Receiving Branch Transfer – Gift | HQOW + ROW | [15 empty] | KK
81 | Inventory Management | Sending Branch Transfer | Sending Branch Transfer | HQOW + ROW | [15 empty] | KK
82 | Inventory Management | Sending Branch Transfer – Gift | Sending Branch Transfer – Gift | HQOW + ROW | [15 empty] | KK
83 | Inventory Management | Stock take adjustment | Stock take adjustment | HQOW + ROW | [15 empty] | KK
84 | Inventory Management | Stock take adjustment authorization | Stock take adjustment authorization | HQOW + ROW | [15 empty] | KK
85 | FAM Transactions | Manage CIP Register | CIP Register | HQOW + FAM
86 | FAM Transactions | Posting CIP Transfer | Posting CIP Transfer | HQOW + FAM
87 | FAM Transactions | Manage FA Register | Manage FA Register | HQOW + FAM
88 | FAM Transactions | FA Disposal & Write Off | FA Disposal & Write Off | HQOW + FAM
89 | FAM Transactions | Depreciation GL Mapping | Depreciation GL Mapping | HQOW + FAM
90 | FAM Transactions | Create GL Journal | GL Journal | HQOW + FAM
91 | FAM Transactions | GL Journal Authorization | GL Journal Authorization | HQOW + FAM
92 | Process | Auto Booking FA Disposal & Write Off | Auto Booking FA Disposal | FAM
93 | Process | FA Depreciation monthly | FA Depreciation monthly | FAM
94 | Purchase Management | AP Payment | AP Payment | HQOW + ROW | [15 empty] | Santhosh
95 | Sales Management | Customer Return | Customer Exchange (Same Price) | HQOW + ROW
96 | Sales Management | Customer Return | Customer Exchange (different price) | HQOW + ROW
97 | Sales Management | Customer RMA Authorization | Customer RMA Authorization | HQOW + ROW
98 | Sales Management | Manage Attribute Combinations | Manage Attribute Combinations | ROW
99 | Sales Management | Manage SO Campaigns | Manage SO Multi Campaigns | ROW
100 | Inventory Management | Manage Transport Manifest | Manage Transport Manifest | ROW
101 | Inventory Management | MEMO: Short Dated Inventory Control – Scheduler | MEMO: Short Dated Inventory Control | ROW
102 | Sales Management | Order delivery Plan Report | Order delivery Plan Report | ROW
103 | Inventory Management | Physical Inventory Authorization Gift | Physical Inventory Authorization Gift | HQOW + ROW | [15 empty] | KK
104 | Sales Management | Print Batch DO | Manage DO Ticked check Box | ROW | Form
105 | Sales Management | Print Batch invoice CDI | Print Batch invoice CDI | ROW
106 | Sales Management | Receivables Write Off | Write Off | HQOW
107 | Sales Management | Sales Order | Consignment Type Order | HQOW + ROW
108 | Sales Management | Sales Order | Process Sales Order | ROW
109 | Sales Management | Sales Order | Promotion Order | HQOW + ROW
110 | Sales Management | Sales Order | SG&A Non Register Order | HQOW + ROW
111 | Sales Management | Sales Order | SG&A Register Order | HQOW + ROW
112 | Sales Management | Sales Order | Topline Non Register Order | HQOW + ROW
113 | Sales Management | Sales Order | Topline Register Order | HQOW + ROW
114 | Sales Management | Sales Order | Consignment of Promotion Order (delivery fee) | HQOW + ROW
115 | Inventory Management | Synch-in-Transit | Synch-in-Transit | ROW | Invalid | [14 empty] | KK
116 | Inventory Management | UnPack Package | Unpack Package | ROW | [15 empty] | KK
117 | Sales Management | Validate Import Proposal SKU | Validate Import Proposal SKU | HQOW
118 | Sales Management | P2P Sku Contribution | Manage Contribution Topline Sub proposal Ratio | HQOW
119 | Sales Management | GAAP TOPLINE NTA RATIO REPORT | GAAP TOPLINE NTA RATIO REPORT | HQOW

## Report (hidden)
# | SERVICE BUNDLES | SERVICE REQUEST -MACRO | SERVICE REQUEST -MICRO | HQ/ROW | PARAMETERS | DATA LOADING(PARAMETER WISE) | PRINT FORMAT | PDF FORMAT | XLSX FORMAT | PERIOD | PERFORMANCE-PDF | PERFORMANCE-XlSX | COLUMNS(AWS & CENTRA) | DATA CHECK | OVERALL STATUS | REMARK | COMMENT | TESTED BY | QA APPROVED BY | QA TIME | TICKET ID
1 | Sales Management | List of Commercial Discount report | List of Commercial Discount report | ROW | PASS | PASS | PASS | PASS | PASS | 10 Days | Time – 20 Sec | Time -5 Sec | PASS | New Data – PASS | PASS |  |  | Hari
2 | Purchase Management | Master NTA PO Report | Master NTA PO Report | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Month | Time -8 Sec | Time -5 Sec | PASS | New Data – PASS | PASS |  |  | Hari
3 | Purchase Management | Master NTA PO Change List | Master NTA PO Change List | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Day | Time -1 Min | Time -5 Sec | PASS | New Data – PASS | PASS |  |  | Hari |  | 15 Mins
4 | Master Management | Master Customer Change List_InDirect | Master Customer Change List_InDirect | ROW | PASS | FAIL | PASS | PASS | PASS | 2 Days | Time -1 Min | Time -1 Min | PASS | New Data – Fail | FAIL | 397183 |  | Hari
5 | Master Management | Master Customer Change List_Direct | Master Customer Change List_Direct | ROW | PASS | FAIL | PASS | PASS | PASS | 10 Days | Time -30 Sec | Time -15 Sec | PASS | New Data – Fail | FAIL | 397178 |  | Hari
6 | Master Management | Master Customer Change List_All | Master Customer Change List_All | ROW | PASS | PASS | PASS | PASS | PASS | 10 Days | Time -28 Sec | Time -10 sec | PASS | New Data – PASS | PASS |  |  | Hari
7 | Sales Management | MASTER CREDIT REPORT | MASTER CREDIT REPORT | HQOW + ROW | PASS | PASS | PASS | PASS | Unavailable | 10 Days | Time -30 Sec | Unavailable | PASS | New Data – PASS | PASS | 397167 |  | Hari
8 | Sales Management | MASTER BALANCE BY SALESMAN (MONTHLY) | MASTER BALANCE BY SALESMAN (MONTHLY) | HQOW + ROW | FAIL | FAIL | PASS | PASS | PASS | 2 Days | Time -30 Sec | Time -15 Sec | PASS | New Data – Fail | FAIL | 396873 |  | Hari
9 | Sales Management | MASTER BALANCE BY SALESMAN (DAILY) | MASTER BALANCE BY SALESMAN (DAILY) | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 10 Days | Time -1 Min | Time -20 Sec | PASS | New Data – PASS | PASS |  |  | Hari
10 | Sales Management | MASTER BALANCE BY Customer (MONTHLY) | MASTER BALANCE BY Customer (MONTHLY) | HQOW + ROW | PASS | FAIL | PASS | PASS | PASS | 11 Days | Time -30 Sec | Time -15 Sec | PASS | New Data – PASS | FAIL | 397172 |  | Hari
11 | Sales Management | MASTER BALANCE BY Customer (MONTHLY) | MASTER BALANCE BY Customer (MONTHLY) | HQOW + ROW | PASS | FAIL | PASS | PASS | PASS | 12 Days | Time -30 Sec | Time -15 Sec | PASS | New Data – PASS | FAIL | 397172 |  | Hari
12 | Sales Management | MASTER BALANCE BY Customer (DAILY) | MASTER BALANCE BY Customer (DAILY) | HQOW + ROW | PASS | FAIL | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – Pass | FAIL | 397170 |  | Hari
13 | Sales Management | Master AR Report VAS | Master AR Report VAS | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – Pass | PASS | 397097 |  | Hari
14 | Sales Management | Master AR Report | Master AR Report | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – Pass | PASS | 397096 |  | Hari
15 | Purchase Management | Master AP Report VAS | Master AP Report VAS | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – Pass | PASS | 397050 |  | Hari
16 | Purchase Management | Master AP report | Master AP report | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Day | Time -10 Sec | Time -5 Sec | PASS | New Data – Pass | PASS | 397049 |  | Hari
17 | Purchase Management | Master AP Payment Change List | Master AP Payment Change List | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Day | Time -10 Sec | Time -5 Sec | PASS | New Data – Pass | PASS |  |  | Hari
18 | Master Management | MARKETING CAMPAIGN REPORT | MARKETING CAMPAIGN REPORT | HQOW | PASS | PASS | PASS | PASS | PASS | 4 Days | Time -10 Sec | Time -6 Sec | PASS | New Data – Pass | PASS |  |  | Hari
19 | Master Management | MARKETING CAMPAIGN CHANGE LIST | MARKETING CAMPAIGN CHANGE LIST | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -20 Sec | Time -10 sec | PASS | New Data – Pass | PASS |  |  | Hari
20 | Master Management | Mapping SGA Report | Mapping SGA Report | HQOW | PASS | PASS | PASS | PASS | PASS | As Of Date | Time -20 Min | Time -1 Min | PASS | New Data – Pass | PASS |  |  | Hari
21 | Master Management | MAPPING SGA CHANGE LIST REPORT | MAPPING SGA CHANGE LIST REPORT | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Day | Time -20 Sec | Time -20 Sec | PASS | New Data – PASS | PASS |  |  | Hari |  | 19 Mins
22 | Master Management | Mapping HFM Change List Report | Mapping HFM Change List Report | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Day | Time -30 Sec | Time -20 Sec | PASS | New Data – PASS | PASS |  |  | Hari |  | 15 Mins
23 | Master Management | Mapping D11 Change List report | Mapping D11 Change List report | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Day | Time -15 Sec | Time -10 sec | PASS | New Data – PASS | PASS |  |  | Hari |  | 15 Mins
24 | Purchase Management | Loan Report | Loan Report | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Day | Time -15 Sec | Time -10 sec | PASS | Not used – Report | PASS | 397105 |  | Hari |  | 15 Mins
25 | Sales Management | List of Promotion Sales-Package | List of Promotion Sales-Package | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Day | Time -20 Sec | Time -20 Sec | PASS | New Data – PASS | PASS |  |  | Hari |  | 10 Mins
26 | Sales Management | List of Promotion Sales Gift | List of Promotion Sales Gift | HQOW | PASS | FAIL | PASS | PASS | PASS | 2 Days | Time -5 Sec | Time -3 Sec | FAIL | New Data – Fail | FAIL |  |  | Hari
27 | Sales Management | List of Promotion Sales | List of Promotion Sales | HQOW | PASS | FAIL | PASS | PASS | PASS | 1 Month | Time -5 Sec | Time -3 Sec | FAIL | New Data – Fail | FAIL |  |  | Hari |  | 25 Mins |  | 396948
28 | Sales Management | LIST OF PAYMENT VOUCHER | LIST OF PAYMENT VOUCHER | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -5 Sec | Time -3 Sec | PASS | New Data – PASS | PASS | 397072 |  | Hari
29 | Sales Management | List of Payment Summary Report | List of Payment Summary Report | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -5 Sec | Time -3 Sec | PASS | New Data – PASS | PASS | 397069 |  | Hari |  |  |  | 396863
30 | Sales Management | List Of Invoice Written To Be | List Of Invoice Written To Be | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Month | Time -5 Sec | Time -3 Sec | PASS | Not used – Report | PASS |  |  | Hari |  |  |  | 396861
31 | Purchase Management | List of Import GRN | List of Import GRN | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -5 Sec | Time -3 Sec | PASS | New Data – PASS | PASS | 397065 |  | Hari
32 | Purchase Management | List Of GRN By Company | List Of GRN By Company | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -20 Sec | Time -15 Sec | PASS | New Data – PASS | PASS | 397046 |  | Hari
33 | Purchase Management | List Of GRN By Branch | List Of GRN By Branch | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -20 Sec | Time -15 Sec | PASS | New Data – PASS | PASS | 397047 |  | Hari
34 | Sales Management | List of Goods Returned-Pack | List of Goods Returned-Pack | HQOW | FAIL | PASS | PASS | PASS | PASS | 2 Days | Time -20 Sec | Time -15 Sec | PASS | New Data – Fail | FAIL | 397194 |  | Hari
35 | Sales Management | List of Goods Returned | List of Goods Returned | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -20 Sec | Time -15 Sec | PASS | New Data – PASS | FAIL | 397056 | Job fail | Hari
36 | Inventory Management | List of Goods issuing Note - Branch Transfer | List of Goods issuing Note - Branch Transfer | HQOW | PASS | PASS | PASS | PASS | PASS | 3 Days | Time -20 Sec | Time -15 Sec | Report not found | Report not found | PASS |  |  | Hari
37 | Inventory Management | List Of Goods Issue Note | List Of Goods Issue Note | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -5 Sec | Time -3 Sec | PASS | New Data – PASS | PASS | 397078 |  | Hari
38 | Purchase Management | List Of GIT Import | List Of GIT Import | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Day | Time -29 Sec | Time -25 Sec | PASS | New Data – PASS | PASS | 397044 |  | Hari
39 | Accoutinh Management | LIST OF GIT AND ACCURAL GIFT | LIST OF GIT AND ACCURAL GIFT | HQOW | PASS | FAIL | PASS | PASS | PASS | 1 Month | Time -29 Sec | Time -25 Sec | PASS | FAIL | FAIL |  | 396798 | Hari
40 | sales Management | List of Discount Invoice Report | List of Discount Invoice Report | HQOW | PASS | FAIL | PASS | PASS | PASS | 1 Month | Time -35 Sec | Time -30 Sec | PASS | FAIL | FAIL |  | 396784 | Hari |  | 30 Mins
41 | sales Management | LIST OF COMMERCIAL DISCOUNT | LIST OF COMMERCIAL DISCOUNT | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 2 Month | Time -35 Sec | Time -30 Sec | PASS | New Data – PASS | PASS | 397161 |  | Hari
42 | sales Management | Invoice VAT In | Invoice VAT In | HQOW | PASS | FAIL | PASS | PASS | PASS | 10 Days | Time –3 Sec | Time – 2 Sec | PASS | FAIL | FAIL |  | 396770 | Hari
43 | sales Management | Invoice Status Report | Invoice Status Report | HQOW | PASS | FAIL | PASS | PASS | PASS | 10 Days | Time – 5 Sec | Time – 4 Sec | PASS | New Data – Fail | FAIL |  | 396754 | Hari |  | 10 Mins
44 | sales Management | INVOICE NOT REALIZED GAIN/LOSS | INVOICE NOT REALIZED GAIN/LOSS | HQOW | PASS | PASS | PASS | PASS | PASS | As Of Date | Time – 5 Sec | Time – 4 Sec | PASS | New Data – PASS | PASS |  |  | Hari
45 | sales Management | Invoice Detail & Margin | Invoice Detail & Margin | ROW | PASS | PASS | PASS | PASS | Fail | 10 Days | Time – 5 Sec | Time – 4 Sec | FAIL | New Data – PASS | FAIL | 397113 |  | Hari
46 | Inventory Management | INVENTRY IN GIFT | INVENTRY IN GIFT | HQOW | PASS | FAIL | PASS | PASS | PASS | 10 Days | Time – 5 Sec | Time – 4 Sec | FAIL | New Data – Fail | FAIL |  |  | Hari
47 | Inventory Management | Inventory Write off Report | Inventory Write off Report | HQOW | PASS | FAIL | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | FAIL | New Data – Fail | FAIL |  |  | Hari
48 | Inventory Management | INVENTORY VALUATION REPORT | INVENTORY VALUATION REPORT | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 397043 |  | Hari
49 | Inventory Management | Inventory Transaction Report | Inventory Transaction Report | HQOW | PASS | PASS | PASS | PASS | PASS | 3 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 397107 |  | Hari
50 | Inventory Management | INVENTORY SHELF LIFE REPORT | INVENTORY SHELF LIFE REPORT | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 397054 |  | Hari
51 | Inventory Management | INVENTORY PROVISION REPORT | INVENTORY PROVISION REPORT | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 397053 |  | Hari
52 | Inventory Management | INVENTORY OUT REPORT COMPANY | INVENTORY OUT REPORT COMPANY | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 397197 |  | Hari
53 | Inventory Management | INVENTORY OUT REPORT BRANCH | INVENTORY OUT REPORT BRANCH | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 396996 |  | Hari
54 | Inventory Management | INVENTORY OUT GIFT | INVENTORY OUT GIFT | HQOW | PASS | FAIL | PASS | PASS | PASS | 3 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – Fail | FAIL | 397190 |  | Hari
55 | Inventory Management | INVENTORY INOUTBY COMPANY | INVENTORY INOUTBY COMPANY | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 397041 |  | Hari
56 | Inventory Management | INVENTORY INOUTBY BRANCH | INVENTORY INOUTBY BRANCH | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 397040 |  | Hari
57 | Inventory Management | INVENTORY INOUT GIFT | INVENTORY INOUT GIFT | HQOW | PASS | FAIL | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | FAIL | New Data – Fail | FAIL | 397196 |  | Hari
58 | Inventory Management | INVENTORY IN REPORT COMPANY | INVENTORY IN REPORT COMPANY | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 396995 |  | Hari
59 | Inventory Management | INVENTORY IN REPORT BRANCH | INVENTORY IN REPORT BRANCH | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 396994 |  | Hari
60 | Inventory Management | Inventory Card Report (Branch) | Inventory Card Report (Branch) | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 397067 |  | Hari
61 | Inventory Management | Inventory Card Report | Inventory Card Report | HQOW | PASS | PASS | PASS | PASS | PASS | 5 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS |  |  | Hari
62 | sales Management | Internal Revenue Report | Internal Revenue Report | HQOW | PASS | PASS | PASS | PASS | PASS | 2016 | Time -10 Sec | Time -5 Sec | PASS | Not used – Report | PASS | 397101 |  | Hari
63 | sales Management | Detail AR Report VAS | Detail AR Report VAS | HQOW | PASS | FAIL | PASS | PASS | PASS | 2 Days | Time -20 Sec | Time -10 sec | FAIL | New Data – Fail | FAIL | 396989 |  | Hari
64 | Sales Management | Detail AR report | Detail AR report | HQOW | PASS | FAIL | PASS | PASS | PASS | 2 Days | Time -20 Sec | Time -10 sec | FAIL | New Data – Fail | FAIL | 396988 |  | Hari
65 | Purchase Management | Detail AP Report VAS | Detail AP Report VAS | HQOW | PASS | FAIL | PASS | PASS | PASS | 2 Days | Time -20 Sec | Time -10 sec | PASS | New Data – Fail | FAIL | 396968 | New Data not loading the report after reload th e MV | Hari
66 | Purchase Management | Detail AP report | Detail AP report | HQOW | PASS | FAIL | PASS | PASS | PASS | 2 Days | Time -20 Sec | Time -10 sec | PASS | New Data – Fail | FAIL |  | New Data not loading the report after reload th e MV, NTA AP Invoice | Hari

## Master (hidden)
# | SERVICE BUNDLES | SERVICE REQUEST -MACRO | SERVICE REQUEST -MICRO | HQ/ROW | FIELD’S | TAB | CREATE | UPDATE/EDIT | DELETE | PERFORMANCE | OVERALL STATUS | REMARK | COMMENT | TEST DATA | TESTED BY | QA APPROVED BY | QA TIME | TICKET ID | START DATE | END DATE
77 | Master Management | Product Stage | Product Stage | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 5 Sec | PASS | [6 empty] | 397239 | 2024-07-24
20 | Master Management | Document Base Type | Document Base Type | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 6 Sec | PASS | [6 empty] | 397247 | 2024-07-24
21 | Master Management | Document Sequence | Define Document Sequence | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 5 Sec | PASS | [6 empty] | 397248 | 2024-07-24
22 | Master Management | Document Type | Define Document Type | HQOW + ROW + FAM | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397251 | 2024-07-24
24 | Master Management | GIFT PRODUCT | GIFT PRODUCT | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397241 | 2024-07-24
25 | Master Management | GL Category | GL Category | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397252 | 2024-07-24
101 | Master Management | User | Define User | HQOW + ROW | FAIL | FAIL | PASS | PASS | PASS | 3 Sec | FAIL |  | 2 Tab Missing , One Field missing |  | . |  |  | 397267 | 2024-07-25
82 | Master Management | RMA CATEGORY | RMA CATEGORY | HQOW + ROW | PASS | PASS | PASS | PASS | FAIL | 3 Sec | FAIL | [6 empty] | 397271 | 2024-07-25
83 | Master Management | Role | Define Role | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397268 | 2024-07-25
84 | Master Management | Role | Define Role Access | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397277 | 2024-07-25
85 | Master Management | Sales Channel | Sales Channel | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397284 | 2024-07-25
86 | Master Management | Sales Person | Sales Rep Info | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397289 | 2024-07-25
87 | Master Management | Sales Region Mapping | Define Sales Region | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397290 | 2024-07-25
90 | Master Management | Scheduler | Email Configuration | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397292 | 2024-07-25
91 | Master Management | Scheduler | Manage Scheduler | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 4 Sec | PASS | [6 empty] | 397296 | 2024-07-25
92 | Master Management | Session Audit | Session Audit | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 4 Sec | PASS | [6 empty] | 397301 | 2024-07-25
100 | Master Management | UOM Group | UOM Group | HQOW + ROW | FAIL | FAIL | PASS | PASS | PASS | 4 Sec | FAIL | [6 empty] | 397305 | 2024-07-25
109 | Master Management | Manage Item List | Manage Item List | ROW | PASS | PASS | PASS | PASS | PASS | 4 Sec | PASS | [6 empty] | 397309 | 2024-07-25
26 | Master Management | Group of Attributes | Group of Attributes | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397311 | 2024-07-25
29 | Master Management | LOCATION | LOCATION | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397312 | 2024-07-25
32 | Master Management | Manage Activity | Manage Activity | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 4 Sec | PASS | [6 empty] | 397314 | 2024-07-25
33 | Master Management | Manage Area Territory Mapping | Manage Area Territory Mapping | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397316 | 2024-07-25
65 | Master Management | Product | Deactivate Product | HQOW + ROW | PASS | FAIL | PASS | PASS | PASS | 4 Sec | FAIL | [6 empty] | 397318 | 2024-07-25

## Print Format
# | SERVICE BUNDLES | SERVICE REQUEST -MACRO | SERVICE REQUEST -MICRO | HQ/ROW | VERIFY PRINT FORMAT | VERIFY DATA LOADING | OVERALL STATUS | COMMENT | TEST DATA | TESTED BY | QA APPROVED BY | QA TIME | TICKET ID | START DATE | END DATE
21 | Sales Management | Manage DO | Manage DO Print – R6 -I | ROW
22 | Sales Management | Manage DO | Manage DO Print – R6 -II | ROW
23 | Sales Management | Manage DO | Manage DO Print – R6 -III | ROW
24 | Sales Management | Manage DO | Manage DO Print – R6 -IV | ROW
25 | Sales Management | Manage DO | Manage DO Print – R7 -I | ROW
26 | Sales Management | Manage DO | Manage DO Print – R7 -II | ROW
27 | Sales Management | Manage DO | Manage DO Print – R7 -III | ROW
28 | Sales Management | Manage DO | Manage DO Print – R7 -IV | ROW
| Purchase Management | Purchase Order
| Purchase Management | Purchase Order
| Purchase Management | Purchase Order
| Purchase Management | Purchase Order

## Jobs (hidden)
# | SERVICE BUNDLES | SERVICE REQUEST -MACRO | SERVICE REQUEST -MICRO | HQ/ROW | JOB DESCRIPTION | VERIFY SCHEDULER RUNNING | DATA CHECK | TIME TAKEN | OVERALL STATUS | COMMENT | TEST DATA | TESTED BY | QA APPROVED BY | QA TIME | TICKET ID | START DATE | END DATE
1 | Sales Managenment | Invoice Write Off Scheduler 1 | Invoice Write Off Scheduler 1 | ROW | Writeoff invoices for Amount <=1000 | PASS | PASS | 3 Sec | PASS |  |  | Hari |  | 30 Mins | 397430 | 2024-07-29 | 2024-07-29
2 | Sales Managenment | Invoice Write Off Scheduler 2 | Invoice Write Off Scheduler 2 | ROW | Writeoff invoices for Amount <=1000 | PASS | PASS | 3 Sec | PASS |  |  | Hari |  | 30 Mins | 397437 | 2024-07-29 | 2024-07-29
3 | Accounting Management | UnAlloPayAmtAcct | UnAlloPayAmtAcct | HQOW | UnAlloPayAmtAcct | PASS | PASS | 3 Sec | PASS |  |  | Hari |  | 1 Hour | 397450 | 2024-07-29 | 2024-07-29
4 | Accounting Management | UnAllocatedPayment | UnAllocatedPayment | HQOW | 1. UnAllocatedPayment is typically used to temporarily hold payments that haven’t been assigned to specific invoices or accounts. 2. It helps to keep track of funds untill they are properly allocated or not. | PASS | PASS | 3 Sec | PASS |  |  | Hari |  | 1 Hour | 397457 | 2024-07-29 | 2024-07-29
5 | Accounting Management | Reversal Accrual Monthly | Reversal Accrual Monthly | ROW | Create reversal entry for Accrual journals | PASS | PASS | 4 Sec | PASS |  |  | Hari |  | 1 Hour | 397475 | 2024-07-30 | 2024-07-30
6 | Accounting Management | GL Accrual Reversal Monthly | GL Accrual Reversal Monthly | ROW | Create reversal entry for Ratio adjustments journals | PASS | PASS | 5 Sec | FAIL |  |  | Hari |  | 1 Hour | 397478 | 2024-07-30 | 2024-07-30
7 | Accounting Management | GL Detail | GL Detail | HQOW | GL Detail refers general ledger. It include individual entries for things like sales, purchases, expenses, and other financial activities. | PASS | PASS | 5 Sec | PASS |  |  | Hari |  | 1 Hour | 397483 | 2024-07-30 | 2024-07-30
8 | Accounting Management | GL Detail CHILD (It will run auto after parent job) | GL Detail CHILD (It will run auto after parent job) | HQOW | GL Detail refers general ledger. It include individual entries for things like sales, purchases, expenses, and other financial activities. | PASS | PASS | 5 Sec | PASS |  |  | Hari |  | 1 Hour | 397484 | 2024-07-30 | 2024-07-30
9 | Accounting Management | ViewAllocation | ViewAllocation | HQOW | 1. ViewAllocation – helps to view how funds are distributed across various categories or accounts. 2. This report helps to know the payments assigned to specific invoices or accounts. | PASS | PASS | 5 Sec | PASS |  |  | Hari |  | 1 Hour | 397485 | 2024-07-30 | 2024-07-30
10 | Accounting Management | BpartnerHistory_Inout | BpartnerHistory_Inout | HQOW | BpartnerHistory_Inout record hepls in documenting all significant interactions, transactions, communications, and changes over time. | PASS | PASS | 5 Sec | PASS |  |  | Hari |  | 1 Hour | 397486 | 2024-07-30 | 2024-07-30
11 | Masters | CUSTOMERSERVICEKPI | CUSTOMERSERVICEKPI | HQOW | CUSTOMERSERVICEKPI- It refers Customer service key performance indicators and metrics used to evaluate the effectiveness of a company’s customer service KPI. It includes Customer satisfaction, Customer retention rate, Resolution time, etc. | PASS | PASS | 5 Sec | PASS |  |  | Hari |  | 1 Hour | 397500 | 2024-07-30 | 2024-07-30
12 | Masters | Bpartner History CHILD 1 | Bpartner History CHILD 1 | HQOW | 1. It refers to a record of interactions, transactions, and engagements with specific entities that the organization considers partners. 2. It helps to managing and maintaining Bpartners history. | PASS | PASS | 5 Sec | PASS |  |  | Hari |  | 30 Mins | 397648 | 2024-07-31 | 2024-07-31
13 | Masters | Bpartner History CHILD 2 | Bpartner History CHILD 2 | HQOW | 1. It refers to a record of interactions, transactions, and engagements with specific entities that the organization considers partners. 2. It helps to managing and maintaining Bpartners history. | PASS | PASS | 5 Sec | PASS |  |  | Hari |  | 30 Mins | 397672 | 2024-07-31 | 2024-07-31
14 | Inventory Management | Inventory Transaction | Inventory Transaction | HQOW | Inventory Transaction | PASS | PASS | 5 Sec | PASS |  |  | Hari |  | 30 Mins | 397737 | 2024-07-31 | 2024-07-31
15 | Synchronization Mgmt | Document Sequence update | Sync data cleanup | HQOW | Sync data cleanup 7 days once | PASS | PASS |  | PASS |  |  | Hari |  | 20 Mins | 397715 | 2024-08-01 | 2024-08-01
16 | Masters | Synch from HQ to Branches and FAM | Synch from HQ to Branches and FAM | HQOW | Masters(Product,Pricelist, Role etc) | PASS | PASS |  | PASS |  |  | Hari |  | 20 Mins | 397740 | 2024-08-01 | 2024-08-01
17 | Sales Managenment | DO Billing Cut-Off | DO Billing Cut-Off | ROW | Repost DO which are created after billing cutoff Unrevenuce account | PASS | PASS | 10 Sec | PASS |  |  | Hari |  | 2 Hours | 397748 | 2024-08-01 | 2024-08-01
18 | Sales Managenment | Invoice Billing Cut-Off | Invoice Billing Cut-Off | ROW | Repost Invoices which are created after billing cutoff | PASS | PASS | 10 Sec | FAIL |  |  | Hari |  | 2 Hours | 397766 | 2024-08-01 | 2024-08-01
19 | Masters | Document Sequence update | Document Sequence update | HQOW | Document sequence update First of Month | PASS | PASS | 20 Sec | PASS |  |  | Hari |  | 2 Hours | 397789 | 2024-08-01 | 2024-08-01
20 | Purchase Management | Import HSBC Acknowledgement | Import HSBC Acknowledgement | ROW | Complete payments based on Acknowledge received from HSBC | PASS | PASS | 20 Sec | PASS |  |  | Hari |  | 2 Hours | 397798 | 2024-08-01 | 2024-08-01
21 | Masters | SKU Contribution% Topline Scheduler | SKU Contribution% Topline Scheduler | HQOW | Allocate the SKU % in Campaign mapped Trade Products 1.Allocate the SKU % in Campaign mapped NTA Products. 2.Allocation calculated by Campaign formulas. | PASS | FAIL | 5 Sec | FAIL |  |  | Hari |  | 1 Hour | 398010 | 2024-08-08 | 2024-08-08
22 | Payment AP | Import HSBC Acknowledgement | Import HSBC Acknowledgement | HQOW | Import Ack file from HSBC to complete Payments 1.Import Ack file from HSBC to complete Payments 2.Compiere system will complelte the AP Payments automatically via xml file Acknowledgement. | PASS | PASS | 4 Sec | PASS |  |  | Hari |  | 2 Hours | 397798 | 2024-08-08 | 2024-08-08
23 | Payment AP | HSBC File Encryption | HSBC File Encryption | HQOW | Encrypt XML file for export into HSBC 1.Encrypt XML file for export into HSBC. 2.All The AP Payment sent to HSBC as xml file. | PASS | FAIL | 5 Sec | FAIL |  |  | Hari |  | 1 Hour | 398012 | 2024-08-08 | 2024-08-08
24 | Sales Managenment | Import DMS Sales Order | Export Reversed DMS Order | ROW | 2.Export Reversed DMS orders invoice to DMS system. 2.DMS get the data from ROW for Reversed invoices. | HOLD | HOLD | 5 Sec | FAIL |  |  | Hari |  | 30 Mins | 398553 | 2024-08-14 | 2024-08-14

## Integration (hidden)
# | SERVICE BUNDLES | SERVICE REQUEST -MACRO | SERVICE REQUEST -MICRO | HQ/ROW | VERIFY PROCESS | DATA CHECK | TIME TAKEN | OVERALL STATUS | COMMENT | TEST DATA | TESTED BY | QA APPROVED BY | QA TIME | TICKET ID | START DATE | END DATE
1 | Master Management | TMS PROGRAM MAPPING | TMS PROGRAM MAPPING | HQOW | PASS | PASS | 2 SEC | PASS | [5 empty] | 397878 | 2024-08-05 | 2024-08-05
2 | Sales Management | TMS Interface Log | TMS Interface Log | ROW | FAIL | FAIL | 3 SEC | FAIL | [5 empty] | 397882 | 2024-08-05 | 2024-08-05
3 | Import & Callout & Export | IMPORT SUB BUDGET | IMPORT SUB BUDGET | HQOW | FAIL | FAIL | 4 SEC | FAIL | [5 empty] | 397889 | 2024-08-05 | 2024-08-05
4 | Import & Callout & Export | Import Sub Proposal | Import Sub Proposal | HQOW | PASS | PASS | 6 SEC | PASS | [5 empty] | 397900 | 2024-08-05 | 2024-08-05
5 | Purchase Management | HSBC File Encryption | HSBC File Encryption | HQOW | FAIL | FAIL | 6 SEC | FAIL | [5 empty] | 397974 | 2024-08-07

## Import & Export (hidden)
# | SERVICE BUNDLES | SERVICE REQUEST -MACRO | SERVICE REQUEST -MICRO | HQ/ROW | VERIFY FORMAT | VERIFY TEMP SCREEN | DATA IN MAIN SCREEN | SINGLE DATA IMPORT | MULTIPLE DATA IMPORT | TIME TAKKEN | OVERALL STATUS | COMMENT | TEST DATS | TESTED BY | QA APPROVED BY | QA TIME | TICKET ID | START DATE | END DATE
1 | Import & Callout & Export | Import Payment netoff | Import Payment netoff | HQOW | PASS | PASS | PASS | PASS | PASS | Single Data : 03 Sec Muliple Data(96) – 10 Sec | PASS | [5 empty] | 397923 | 2024-08-06 | 2024-08-06
2 | Import & Callout & Export | IMPORT STANDARD COST PRICE | IMPORT STANDARD COST PRICE | HQOW | PASS | PASS | PASS | PASS | PASS | Single Data : 03 Sec Muliple Data(20) – 8 Sec | PASS | [5 empty] | 397927 | 2024-08-06 | 2024-08-06
3 | Import & Callout & Export | Import Internal Transfer Invoice | Import Internal Transfer Invoice | ROW | PASS | PASS | FAIL | PASS | PASS | Single Data : 03 Sec Muliple Data(15) – 8 Sec | FAIL | Data showing read only |  |  |  |  | 397935 | 2024-08-06 | 2024-08-06
4 | Import & Callout & Export | Import Payment(HSBC) | Import Payment(HSBC) | ROW | PASS | FAIL | HOLD | HOLD | FAIL | HOLD | FAIL | Temp screen missing |  |  |  |  | 397939 | 2024-08-06 | 2024-08-06
5 | Import & Callout & Export | Import Products | Import Products | ROW: HQOW; PASS: Not Used; HOLD: Not Used; FAIL: Not Used | [6 empty] | 2024-08-06 | 2024-08-06
6 | Import & Callout & Export | IMPORT NTA GOODS RECEIPT | IMPROT NTA GOODS RECEIPT | HQOW | PASS | PASS | PASS | PASS | PASS | Single Data : 5 Sec Muliple Data(200) – 5 Min 20 Sec | PASS | [5 empty] | 397949 | 2024-08-07 | 2024-08-07
7 | Import & Callout & Export | Import FA Register | Import FA Register | FAM | PASS | FAIL | HOLD | FAIL | FAIL | HOLD | FAIL | [5 empty] | 397951 | 2024-08-07 | 2024-08-07
8 | Import & Callout & Export | Import CIP Register | Import CIP Register | FAM | PASS | PASS | PASS | PASS | PASS | Single Data : 3 Sec Muliple Data(3) – 5 Sec | PASS | [5 empty] | 397957 | 2024-08-07 | 2024-08-07

## Form (hidden)
# | SERVICE BUNDLES | SERVICE REQUEST -MACRO | SERVICE REQUEST -MICRO | HQ/ROW | VERIFY PARAMETER | VERIFY FILTER | VERIFY SINGLE PROCESS | VERIFY MULTIPLE PROCESS | VERIFY FOOTER COLUMN | OVERALL STATUS | COMMENT | TEST DATA | TESTED BY | QA APPROVED BY | QA TIME | TICKET ID | START DATE | END DATE
1 | FORM | Batch Complete Commercial Discount | Batch Complete Commercial Discount | HQOW | PASS | PASS | PASS | PASS | FAIL | FAIL | Overhall converted amount value shows wrong |  | Hari |  | 2:00 | 398648 | 2024-08-20 | 2024-08-20
2 | FORM | Reject Commercial Discount | Reject Commercial Discount | HQOW | PASS | PASS | PASS | PASS | PASS | PASS |  |  | Hari |  | 26:00 | 398649 | 2024-08-20 | 2024-08-20
3 | FORM | Multi VAT Transfer | Multi VAT Transfer | HQOW | PASS | PASS | FAIL | FAIL | PASS | FAIL | Invoice not loading in Multi VAT Trasnfer form |  | Hari |  | 1:00 | 398656 | 2024-08-20 | 2024-08-20
4 | FORM | Generate Treasury Encryption | Generate Treasury Encryption | HQOW | PASS | PASS | FAIL | FAIL | PASS | FAIL | File not exported |  | Hari |  | 1:30 | 398669 | 2024-08-20 | 2024-08-20
5 | FORM | ExportBatch AP City Report | ExportBatch AP City Report | HQOW | PASS | PASS | PASS | PASS | PASS | PASS |  |  | Hari |  | 1:30 | 398676 | 2024-08-21 | 2024-08-21
6 | FORM | Import File Loader | Import File Loader | ROW | PASS | FAIL | PASS | PASS | FAIL | FAIL | Some formats missing |  | Hari |  | 1:30 | 398680 | 2024-08-21 | 2024-08-21
7 | FORM | System Cash Receipt By Salesman | System Cash Receipt By Salesman | ROW | PASS | FAIL | FAIL | FAIL | PASS | FAIL | Process not working |  | Hari |  | 1:30 | 398691 | 2024-08-22 | 2024-08-22
8 | FORM | Re-Print System Receipt By Salesman | Re-Print System Receipt By Salesman | ROW | PASS | PASS | FAIL | FAIL | PASS | FAIL | Process not working |  | Hari |  | 1:30 | 398698 | 2024-08-22 | 2024-08-22
9 | FORM | RePrint Picking List Summary | RePrint Picking List Summary | ROW | PASS | PASS | FAIL | FAIL | PASS | FAIL | Process not working |  | Hari |  | 1:30 | 398701 | 2024-08-22 | 2024-08-22
10 | FORM | Update Customer Confirmation | Update Customer Confirmation | ROW | PASS | PASS | PASS | PASS | PASS | PASS |  |  |  |  | 1:30 | 398705 | 2024-08-23 | 2024-08-23
11 | FORM | Update Invoice Details to TMS | Update Invoice Details to TMS | ROW | PASS | PASS | FAIL | FAIL | PASS | FAIL | Log not created |  | Hari |  | 1:30 | 398724 | 2024-08-23 | 2024-08-23
12 | FORM | Print Batch Invoice | Print Batch Invoice | ROW | PASS | FAIL | PASS | FAIL | PASS | FAIL | Multiple process fail |  | Hari |  | 1:30 | 398726 | 2024-08-23 | 2024-08-23
13 | FORM | Reject Approved Request | Reject Approved Request | ROW | PASS | Not used |  |  | Not used |  |  |  | Hari |  | 1:00 | 398749 | 2024-08-23 | 2024-08-23
14 | FORM | Update System ReceiptNo By Salesman | Update System ReceiptNo By Salesman | ROW | PASS | PASS | FAIL | FAIL | PASS | FAIL | Process not working |  | Hari |  | 1:30 | 398752 | 2024-08-26 | 2024-08-26
15 | FORM | CreateFromPOI | CreateFromPOI | ROW | PASS | PASS | PASS | PASS | PASS | PASS |  |  | Hari |  | 1:30 | 398753 | 2024-08-26 | 2024-08-26
16 | FORM | CreateFromInvoice | CreateFromInvoice | ROW | PASS | PASS | PASS | PASS | PASS | PASS |  |  | Hari |  | 1:30 | 398754 | 2024-08-26 | 2024-08-26
17 | FORM | CreateFromShipment | CreateFromShipment | ROW | PASS | PASS | PASS | PASS | PASS | PASS |  |  | Hari |  | 1:30 | 398760 | 2024-08-26 | 2024-08-26
18 | FORM | Generate Transport Manifest | Generate Transport Manifest | ROW | PASS | PASS | FAIL | FAIL | FAIL | FAIL | Process not working |  | Hari |  | 1:30 | 398769 | 2024-08-26 | 2024-08-26
19 | FORM | Print Batch DO | Print Batch DO | ROW | PASS | PASS | FAIL | FAIL | FAIL | FAIL | Form not released |  | Hari |  | 0:30 | 398521 | 2024-08-26 | 2024-08-26